| Level 8, 447 Collins Street, Melbourne VIC 3000 Australia | Telephone +61 3 8644 3500 |
| --- | --- |
| PO Box 3, Collins Street West VIC 8007 Australia | Facsimile 1300 365 323 (Australia) +61 2 8507 6582 (International) |
|  | hwlebsworth.com.au |

Formal Instrument of Agreement

The Refurbishment of the AHC 
Staff Residential Compound Konedobu, 
Port Moresby, Papua New Guinea
Stages 2-8

Commonwealth of Australia represented by the Overseas Property Office of the Department of Foreign Affairs and Trade (ABN 47 065 634 525)

and

[#Insert]

Formal Instrument of Agreement

| Date | [#Insert date of execution] |
| --- | --- |
| Parties | Commonwealth of Australia represented by the Overseas Property Office of the Department of Foreign Affairs and Trade ABN 47 065 634 525 of R G Casey Building, John McEwen Crescent, Barton, 0221 ACT (Principal) |
|  | [#Insert] (Contractor) together, the Parties. |
| Recitals | The Principal requires the refurbishment of 39 residences of the Konedobu Residences in Port Moresby, Papua New Guinea. The Principal wishes to engage the Contractor to execute and complete the Works and undertake the WUC in relation to the refurbishment described in Recital A in accordance with the Contract. The Contractor agrees to its engagement on the terms set out in the Contract. The Contractor is experienced in the design and construction of work of a nature similar to the WUC. |
| The parties agree, in consideration of, among other things, the mutual obligations contained in this Contract as follows: |  |

Agreed Terms

Definitions

In this Formal Instrument of Agreement, unless stated otherwise, defined terms have the same meaning as in the General Conditions.

Performance

The Principal and the Contractor hereby agree to perform their respective obligations under the Contract to enable all of the Works to be completed in accordance with the Contract.

Without limiting clause 2.1 of this Formal Instrument of Agreement:

the Contractor shall carry out and complete the WUC in accordance with the Contract; and

subject to the terms of the Contract and the due and proper performance of the Contractor's obligations, the Principal shall pay the Contractor all sums under the Contract at the times and in the manner provided for in the Contract.

Contract Documents

The Contract comprises the documents identified in the table below (Contract Documents).

Without limiting any part of the General Conditions, the order of precedence listed in the table below applies if there is any ambiguity, conflict, discrepancy or inconsistency between the documents comprising the Contract or between different parts of any one such document.

| Document Description | Where Found |
| --- | --- |
| Formal Instrument of Agreement | This document |
| General Conditions of Contract for Design and Construct AS4902-2000 as amended (Contract Conditions) | Attached to this document |
| Contract Particulars | Annexure Part A |
| Principal's Project Requirements (including the Preliminary design) | Annexure Part F |
| The remaining Annexures and Attachments to the AS4902-2000 (as amended) and this Agreement | Attached to this document |

The parties agree and acknowledge that a copy of the Contract Conditions marked-up to identify deletions, additions and amendments made, has been made available to them prior to execution of this Formal Instrument of Agreement.

Staging and Phasing

The Works have seven Stages, as follows:

Stage 2: Houses 35 - 39;

Stage 3: Houses 29 - 34;

Stage 4: Houses 23 - 28;

Stage 5: Houses 13 - 16;

Stage 6: Houses 17 - 22;

Stage 7: Houses 1 - 6; and

Stage 8: Houses 7-12.

- The delivery of the Works under this Contract includes two phases, as follows:

    - the Principal enters into the Due Diligence Phase with the Contractor;

during the Due Diligence Phase:

the Contractor will have early involvement in the design, planning, programming and cost planning of the Works; and

a key purpose of Due Diligence Phase is to maximise the achievement of the Project Objectives;

If Delivery Phase Approval is achieved under the Contract, the Principal will elect to proceed with the Delivery Phase;

if Delivery Phase Approval is not achieved under the Contract, the Principal may proceed to have the Works executed by a third party.

Contract Sum

As at the Date of the Contract, the Contract Sum in respect of each Stage is the lump sum set out in the table below plus GST, which is inclusive of all provisional sums, prime cost items, disbursements, expenses (including accommodation, equipment hire, car hire and travel expenses), overheads, profit, taxes and fees of any nature.

| Stage | Due Diligence Phase Price | Delivery Phase Price (ex-Provisional Allowance (Cost)) | Provisional Allowance (Cost) | Contract Sum (Stage) |
| --- | --- | --- | --- | --- |
| Stage 2 | [#Insert] | [#Insert] | [#Insert] | [#Insert] |
| Stage 3 | [#Insert] | [#Insert] | [#Insert] | [#Insert] |
| Stage 4 | [#Insert] | [#Insert] | [#Insert] | [#Insert] |
| Stage 5 | [#Insert] | [#Insert] | [#Insert] | [#Insert] |
| Stage 6 | [#Insert] | [#Insert] | [#Insert] | [#Insert] |
| Stage 7 | [#Insert] | [#Insert] | [#Insert] | [#Insert] |
| Stage 8 | [#Insert] | [#Insert] | [#Insert] | [#Insert] |

- The Contract Sum is not subject to adjustment for rise or fall in the cost of labour, materials or services or fluctuations in import duty or exchange rates, or for additional sales taxes or other taxes or imposts or for any other matter or thing whatsoever affecting the cost to the Contractor of carrying out and completing the Works except as expressly provided in the Contract.

If a schedule of rates is included in the Contract, it is included for the purpose of pricing variations in accordance with clause 36.

Entire Agreement

The Contract Documents constitute the entire agreement between the parties in respect of the Works and the Contract supersedes all previous agreements, undertakings, communications and any tender, whether written or oral, relating to the subject matter of the Contract.

The Contract may be varied only by written instrument executed by both parties.

The Contract may be executed in counterparts and all of those counterparts taken together constitute one and the same instrument.

None of the terms of the Contract shall be varied, waived, discharged or released, except with the prior written consent of the parties.

Warranties and Non-Reliance

The Contractor:

warrants that it has the capacity to enter into this Contract and that it has the skill, technology, human and financial resources necessary to perform its obligations;

warrants that it is experienced in the design and construction of works similar to the Works;

acknowledges that this Contract constitutes the entire agreement between the parties;

warrants that aside from the documents comprised by the Contract, it has not relied upon any representation, statement, information or documentation for the purposes of entering into this Contract;

warrants that it has entered into this Contract based on its own investigations, considerations and determinations; and

acknowledges that the Principal has entered into this Contract based on the Contractor’s warranties and representations.

Parties to give effect to the Contract

The parties agree that they shall do everything reasonably necessary to give effect to the Contract.

If any provision of this Contract is unenforceable, illegal or void then it is severed and the rest of the Contract remains on foot.

Warranties

Each party represents and warrants to the other party that:

It has full power and authority to execute the Contract and to perform its obligations under the Contract;

The Contract has been duly executed by it; and

The obligations undertaken by it and set out in the Contract are enforceable against it in accordance with the terms of the Contract.

- Executed as an agreement

| Signed for and on behalf of the Commonwealth of Australia in the presence of: |  |  |
| --- | --- | --- |
| Signature of witness |  | Signature of Authorised Officer |
| Name of Witness in full |  | Name of Authorised Officer in full |
| Date |  |  |

| Executed by [#Insert] in accordance with section 127(1) of the Corporations Act 2001 (Cth) by: |  |  |
| --- | --- | --- |
| Signature of Director |  | Signature of Director/Company Secretary |
| Full name (print) |  | Full name (print) |
| Date |  | Date |

AS 4902—2000

Amended AS 4902—2000

(Incorporating Amendment No. 1)

Australian Standard™

Amended from General conditions of contract for design and construct

Project: 	AHC Port Moresby PNG -
Konedobu Residences Refurbishment Project - Stages 2-8

Modified by:

Reproduced and modified by HWL Ebsworth Lawyers (ABN 37 246 549 189) (Licensee) under licence CL0922hwle issued by Standards Australia Limited. The Licensee may reproduce and modify this document in accordance with the licence. Any further reproduction is strictly prohibited. All copies of this document must be obtained from the Licensee. Should the end user be interested in reproducing any content of this document, please contact Standards Australia via copyright@standards.org.au.

This Australian Standard was prepared by Committee OB-003, General Conditions of Contract. It was approved on behalf of the Council of Standards Australia on 
7 September 1999. This Standard was published on 27 December 2000.

The following are represented on Committee OB-003:

Association of Consulting Engineers Australia
 Australian Chamber of Commerce and Industry
Australian Procurement and Construction Council
AUSTROADS
Construction Industry Engineering Services Group
Construction Policy Steering Committee
 Electricity Supply Association of Australia
Institution of Engineers, Australia
Institution of Professional Engineers, New Zealand
Law Council of Australia
Master Builders Australia
National Construction Council of the Australian Industry Group
Process Engineers and Constructors Association
Royal Australian Institute of Architects

Keeping Standards up-to-date

Standards are living documents which reflect progress in science, technology and systems. To maintain their currency, all Standards are periodically reviewed, and new editions are published. Between editions, amendments may be issued. Standards may also be withdrawn. It is important that readers assure themselves they are using a current Standard, which should include any amendments which may have been published since the Standard was purchased.

Detailed information about Standards can be found by visiting the Standards Web Shop at www.standards.com.au and looking up the relevant Standard in the on-line catalogue.

Alternatively, the printed Catalogue provides information current at 1 January each year, and the monthly magazine, The Global Standard, has a full listing of revisions and amendments published each month.

Australian StandardsTM and other products and services developed by Standards Australia are published and distributed under contract by SAI Global, which operates the Standards Web Shop.

We also welcome suggestions for improvement in our Standards, and especially encourage readers to notify us immediately of any apparent inaccuracies or ambiguities. Contact us via email at mail@standards.org.au, or write to the Chief Executive, Standards Australia, GPO Box 5420, Sydney, NSW 2001.

This Standard was issued in draft form for comment as DR 97528.

Amended AS 4902—2000

(Incorporating Amendment No. 1)

Australian Standard™

Amended from General conditions of contract for design and construct

First published as AS 4300—1995.
Revised and redesignated AS 4902—2000.
Reissued incorporating Amendment No. 1 (March 2005).

COPYRIGHT

© Standards Australia

All rights are reserved. No part of this work may be reproduced or copied in any form or by any means, electronic or mechanical, including photocopying, without the written permission of the publisher.

Published by Standards Australia, GPO Box 5420, Sydney, NSW 2001, Australia

ISBN 0 7337 3524 X

PREFACE

This Standard was prepared by the Joint Standards Australia/Standards New Zealand Committee OB/3, General Conditions of Contract.

This Standard incorporates Amendment No. 1 (March 2005). The changes required by the Amendment are indicated in the text by a marginal bar and amendment number against the clause, note, table, figure or part thereof affected.

This Standard is the result of a consensus among Australian and New Zealand representatives on the Joint Committee to produce it as an Australian Standard.

AS 4902—2000 General conditions of Contract for design and construct, is a part of the suite of conditions of contract based on AS 4000—1997 General conditions of Contract.

This Standard covers the following types of project procurement methods:

(a)	design and construct;

(b)	design development and construct; and

(c)	design, novate and construct.

If the project procurement method chosen by the Principal is:

(a)	design and construct—the Principal would provide the Principal’s project requirements, would not normally provide a detailed preliminary design and would not require novation;

(b)	design development and construct—the Principal would provide the Principal’s project requirements, would always provide a preliminary design and accordingly would complete Annexure Part A Items 10 and 11;

(c)	design, novate and construct—the Principal would provide the Principal’s project requirements, would always provide a preliminary design, would complete Annexure Part A Items 10 and 11 and would complete Annexure Part A Item 20 stating which subcontract (including consultant’s agreement) or selected subcontract is to be novated to the Contractor.

Subclauses 8.6 and 29.2, prefixed by *, are optional, and may be omitted in the Contract, where necessary, without making consequential amendments but such omission should be clearly shown on the face of the document by striking out these subclauses or indicating clearly in clause 1 of Annexure Part E or elsewhere that they are not to apply. See paragraph (i) of clause 1 for the effect of stating deletions in Annexure Part E.

Warnings

(1)	Users of this Australian Standard are warned that clause 15 (Damage to persons and property other than WUC) does not limit the liability of parties for special, indirect or consequential losses.

This unlimited liability applies notwithstanding any limitations or exclusions permitted under insurance clauses 16A (Insurance of the Works), 16B (Professional indemnity insurance) and 17 (Public liability insurance).

Parties wishing to limit their liability should seek insurance and legal advice before entering a contract under this Standard.

(2)	Principals should ensure that their specific requirements are fully and completely incorporated in the Principal’s project requirements obtaining specialist advice if necessary. Where a Contractor provides a proposed design as part of its tender, the parties should consider whether that design should form part of the preliminary design.

(3)	The risk allocation, drafting, interpretation and construction of this Standard are interrelated. Users who alter the Standard do so at their own risk and should obtain specialist advice as to whether it is suitable for a particular project.

(4)	Contractors should ensure that they satisfy the requirements of payment for unfixed plant and materials.

(5)	Legislation has come into force in some jurisdictions dealing with security of payments. Parties intending to use this Standard should seek expert advice as to their rights and obligations under such legislation.

CONTENTS

Clause 	Title                                                               Page

1 Interpretation and construction of Contract	16

2 Nature of Contract	25

3 Not used	27

4 Not used	27

5 Security	27

6 Due Diligence Phase	28

7 Service of notices	38

8 Contract documents	38

9 Assignment and subcontracting	41

10 Intellectual property rights	42

11 Legislative requirements	42

12 Protection of people and property	43

13 Urgent protection	43

14 Care of the work and reinstatement of damage	43

15 Damage to persons and property other than WUC	44

17 Public liability insurance	46

18 Insurance of employees	46

19 Inspection and provisions of insurance policies	46

20 Superintendent	47

21 Superintendent’s Representative	48

22 Contractor’s representative	48

23 Contractor’s employees and subcontractors	48

24 Site	48

25 Latent conditions	49

26 Not Used	50

27 Cleaning up	50

28 Materials, labour and Construction Plant	51

29 Quality	51

30 Examination and testing	52

31 Working hours	53

32 Programming	53

33 Suspension	54

34 Time and progress	54

35 Defects liability	56

36 Variations	57

37 Payment	58

38 Payment of workers, consultants and subcontractors	60

39 Default or insolvency	60

40 Termination for Convenience	64

41 Not Used	64

42 Notification of Claims	64

43 Dispute resolution	65

44 Waiver of conditions	66

45 Transparency and Accountability Requirements	66

46 Industrial Relations	66

47 Australian Government Building and Construction OHS Accreditation Scheme	67

48 Taxes, Duties and Government Charges	67

48A    Papua New Guinea Duties	67

48B   Goods and Services Tax	68

49 Work Health and Safety	68

50 Key Personnel	69

51 Management Plans	69

52 Audits and Records	70

53 Access to Documents	72

54 Privacy	72

55 Representations Made as Part of Tender	74

56 Representations, Sanctions, Counter Terrorism and Anti-terrorism	74

57 Prohibited Dealings	75

58 Fraud	75

59 Anti-Corruption	78

60 Child Protection	78

61 Preventing sexual exploitation, abuse and harassment (PSEAH)	78

62 Modern Slavery and Human Trafficking	79

63 Environmental Requirements	79

64 Pandemic Relief Event	79

65 Commonwealth Supplier Code of Conduct	80

66 Notification of Significant Events	81

67 Ethical Conduct	82

68 Workplace Gender Equality	82

69 Applicable Laws and Polices	82

Part A	85

Part B	92

Part C	93

Part D	95

Part E	96

Part F	97

Part G	98

Part H	99

STANDARDS AUSTRALIA

Australian Standard

General conditions of contract for design and construct

Interpretation and construction of Contract

|  | In the Contract, except where the context otherwise requires: |
| --- | --- |
| Item | means an Item in Annexure Part A; |
| Annexure | means each annexure to this Contract which forms part of this Contract; |
| Buildability Input | has the meaning in subclause 6.2(a)(ii); |
| Buildability Issue | includes: (a) any aspect of the Preliminary Design which causes a problem, difficulty or complexity relating to: (i) the means, methods or techniques by which the WUC are to be performed at the Site; or (ii) the co-ordination or integration of the WUC at the Site; and (iii) any problem, difficulty or complexity relating to the connection or existence of services to or at the Site; and (b) a Design Error; |
| Certificate of Practical Completion | has the meaning in subclause 34.6; |
| Civil Disturbance | when 20 or more persons act in concert in sustained defiance of government or any institution or corporation on a national scale and those persons: (a) cause severe disruption to the WUC and the progress of the Works, or the Site, or the Contractor’s access to and from the Site; and (b) are not under the effective control of the Contractor or any of its subcontractors, suppliers or agents, but excludes industrial disputation; |
| Claim | includes any claim for an increase in the Contract Sum, for payment of money (including damages) or for an extension of time: (a) under, arising out of or in connection with the Contract, including any Direction of the Superintendent; (b) arising out of or in connection with the WUC, the Works or either party's conduct before the Contract; or (c) otherwise at law or in equity including: (i) by statute; (ii) in tort for negligence or otherwise, including negligent misrepresentation; or (iii) for restitution. |
| Compensable Cause | means: (a) any breach of contract or other wrongful act, default or omission of the Superintendent, the Principal or its consultants, agents or other contractors (not being employed by the Contractor); or (b) those listed in Item 31; |
| Construction Plant | means appliances and things used in the carrying out of WUC but not forming part of the Works; |
| Consultant | means any person engaged by the Contractor to perform consultancy services in connection with WUC and includes any Principal’s consultant whose prior contract is novated to the Contractor under subclause 9.4; |
| Contract | has the meaning in clause 6; |
| Contract Sum (Aggregate) | means the aggregate of the Contract Sums (Stage) as at the relevant date; |
| Contract Sum (Stage) | means the lump sum amounts set out in the Formal Instrument of Agreement consisting of: during the Due Diligence Phase, the Due Diligence Phase Price; and during the Delivery Phase, the Delivery Phase Price; |
| Contractor | means the person bound to carry out and complete WUC; |
| Contractor’s Design Obligations | means all tasks necessary to design and specify the Works required by the Contract, including preparation of the Design Documents (For Construction) and Design Verification and Site Due Diligence; |
| Cost Plan | means the cost plan in Annexure Part G, as amended (with the approval of the Superintendent) under clause 6.5; |
| Date for Delivery Phase Approval | means the date set out in Annexure Part A, as adjusted (if at all) under clause 6.9(b); |
| Date for Practical Completion | means the date in Item 7 as adjusted: - during the Due Diligence Phase under clause #; and during the Delivery Phase under the Contract; |
| Date of the Contract | means the date means the date when the Contract has been executed by both the Contractor and the Principal, as set out in the Formal Instrument of Agreement; |
| Date of Delivery Phase Approval | means the date of the notice under subclause 6.10(a); |
| Date of Practical Completion | means, in respect of a Stage: (a) the date evidenced in a Certificate of Practical Completion as the date upon which Practical Completion was reached; or (b) where another date is determined in any arbitration or litigation as the date upon which Practical Completion was reached, that other date; |
| Deed of Guarantee, Undertaking and Substitution | has the meaning in subclause 5.7; |
| Defects | has the meaning in clause 35 and includes omissions; |
| Defects Liability Period | means the period in Item 32 |
| Delay Costs | has the meaning in subclause 34.9; |
| Delivery Phase | means the period, for each Stage: - commencing on the Date of Delivery Phase Approval; and - ending on the expiry of the last Defects Liability Period; |
| Delivery Phase Approval | means, for each Stage: - any adjustment to (as applicable) the date for commencement of Works on Site, the Delivery Phase Price and the relevant Date for Practical Completion; - any amendments to Annexure Part A and (if applicable) the other documents forming part of the Contract have been agreed and executed by the Contractor in accordance with clause 6.8(c); - the Due Diligence Report has been approved by the Superintendent; - the Contractor has otherwise complied with all of its obligations under the Contract to the extent applicable before the Date of Delivery Phase Approval and satisfied each condition precedent to Delivery Phase Approval; and - the Principal has determined (in its absolute discretion) to proceed with the Contractor from the Due Diligence Phase to the Delivery Phase; |
| Delivery Phase Price | means the Delivery Phase Price, including the Provisional Allowance (Cost) for each Stage as adjusted from time to time, by any additions or deductions required to be made under the Contract; |
| Design Error | means any error, omission, ambiguity, inadequacy, inconsistency, incompleteness or lack of co-ordination or integration of, between or in any documents which make up the Preliminary Design; |
| Design Documents (for Construction) | means the drawings, specifications and other information, samples, models, patterns and the like required by the Contract to be created by the Contractor for the construction of the Works and which have not been rejected by the Superintendent under subclause 8.3; |
| Design Verification | means the Due Diligence of the Design Documents undertaken by the Contractor under clause 6; |
| Direction | includes agreement, approval, assessment, authorisation, certificate, decision, demand, determination, explanation, instruction, notice, order, permission, rejection, request or requirement; |
| Dispute | has the meaning in clause 43; |
| Due Diligence | means the due diligence of the Preliminary Design and the Site required under subclause 6.1(b). |
| Due Diligence Activities | means the WUC to be performed in the Due Diligence Phase, including as described in, or reasonably to be inferred from, the Principal's Project Requirements and the other requirements of the Contract; |
| Due Diligence Input | means: - Buildability Input; Innovation Input; and Risk Reduction Input; |
| Due Diligence Phase | means, for each Stage, the period: - commencing on the Date of the Contract; and - ending on the earlier of: (i) the Date of Delivery Phase Approval; and (ii) the date of a notice under clause 6.9 (b)(ii). |
| Due Diligence Phase Price | - means the amounts for each Stage specified in Annexure Part A as adjusted, from time to time, by any additions or deductions required to be made under the Contract; |
| Due Diligence Report | - means a report: - in a form reasonably required by the Superintendent; - containing all Due Diligence Input to be implemented by the Contractor in finalising the Preliminary Design at the start of the Delivery Phase; and - approved by the Superintendent under subclause 6.3. |
| EOT (from ‘extension of time’) | has the meaning in subclause 34.3; |
| Excepted Risk | has the meaning in subclause 14.3; |
| Final Certificate | has the meaning in subclause 37.4; |
| Final Payment | has the meaning in clause 37.4; |
| Final Payment Claim | means the final payment claim referred to in subclause 37.4; |
| Force Majeure | means: war, invasion or act of foreign enemies, hostilities (whether war be declared or not), Civil Disturbance, martial law or confiscation by order of any government or public authority; ionising radiation or contamination by radioactivity from any nuclear fuel or from any nuclear waste, from the combustion of nuclear fuel, radioactive, toxic, explosive or other hazardous properties of any explosive assembly or nuclear component; fire, explosion or flood at or transgressing on to the Site, not caused or contributed to by the Contractor or any of its associates, where the Contractor can demonstrate that all reasonable preventative measures were taken (having regard to the nature of the Site and the Work, as the case may be) to minimise the cause and effect of the fire, explosion or flood on the performance of its obligations under this Contract; lightning, hurricane, cyclone, earthquake, natural disaster, tsunami, drought declared as a state of emergency or mudslide; or a pandemic declared by the World Health Organisation or any additional Legislative Requirement imposed by a statutory authority in the relevant jurisdiction relating to COVID-19 that arises after the Date of the Contract and has a material impact on the performance of the Contract, - which (either separately or together) directly causes a party to be unable to perform all or a material part of its obligations (other than an obligation to pay money) under this Contract where the event or its consequences could not have been prevented by the exercise of a standard of care and diligence consistent with that of a prudent person undertaking the obligations under this Contract and where the event or its consequences were not otherwise caused or contributed to by the failure by a party to comply with its obligations under this Contract, excluding; all forms of industrial action; and wet or inclement weather which does not amount to an event referred to in paragraph (d) of this definition or to flood referred to in paragraph (c) of this definition |
| Formal Instrument of Agreement | means the document of that title to which these General Conditions of Contract are attached; |
| Host Nation | means the country specified in Annexure Part A. |
| Inclement Weather | means the existence of or effect of rain or abnormal climatic conditions including but not limited to hail, snow, cold, high wind, severe dust storm, extreme high temperature or any combination thereof by virtue of which it is either not reasonable or not safe for employees of the Contractor exposed thereto to continue working whilst the same prevail, or which is the sole cause of delay in the delivery of plant or materials used in the performance of the Works to the Site; |
| Indicative Delivery Phase Price | means the amount for each Stage set out in the Contract Particulars as at the Award Date. |
| Innovation Input | means all input into the Preliminary Design which a prudent, competent and experienced contractor (having been given the opportunity to undertake the Due Diligence which the Contractor has been given) would reasonably have provided to the Principal to ensure that the Project Objectives are maximised in the design of the Works, including the cost planning recommendations required under clause 6.5(a)(ii) and the programming recommendations required under clause 6.6(a)(ii). |
| Intellectual Property Right | means any patent, registered design, trademark or name, copyright or other protected right; |
| Latent Condition | has the meaning in subclause 25.1; |
| Legislative Requirement | includes: (a) Acts, Ordinances, regulations, by-laws, orders, awards and proclamations of the jurisdiction where WUC or the particular part thereof is being carried out; (b) certificates, licences, consents, permits, approvals and requirements of organisations having jurisdiction in connection with the carrying out of WUC; and (c) fees and charges payable in connection with the foregoing; |
| Master Program | means the Principal's program for all Stages and other events, as set out in Annexure Part H; |
| Management Plans | includes the Quality Plan; the Work Health and Safety Plan, the Environment Plan, the Administration and Site Management Plan, the Risk Management Plan, the Test and Acceptance Plan and the Program, as set out in the Principal's Project Requirements; |
| Practical Completion | means, in respect of a Stage, that stage in the carrying out and completion of WUC when the Superintendent determines that: - the Stage is complete except for minor Defects: (i) which do not prevent the Stage from being reasonably capable of being used for the purposes set out in, or reasonably to be inferred from, the Contract; (ii) which the Superintendent determines the Contractor has reasonable grounds for not promptly rectifying; and (iii) the rectification of which will not prejudice the convenient use of the Stage, including the convenient occupation by residents of the residences constituting the Stage; all Tests which are required by the Contract or the relevant manufacturer to be carried out and passed before the Stage reaches Practical Completion have been carried out and passed to the satisfaction of the Superintendent; documents and other information required under the Contract which, in the Superintendent’s opinion, are essential for the use, operation and maintenance of the Stage have been supplied; all ‘as constructed drawings' required under the Contract have been provided and accepted by the Superintendent; all services have been connected, commissioned and are operational; all rubbish, surplus material, water, temporary structures, offices and minor items of plant and equipment have been removed from the Site so as to leave the site in a clean and tidy condition, except those items to which the Superintendent consents in writing remaining on the site for the purpose of performing Work during the Defects Liability Period; the Contractor has delivered to the Superintendent evidence of the satisfaction of all Legislative Requirements necessary for the lawful occupation and use of the Stage for the purposes set out in, or reasonably to be inferred from, the Contract, including but not limited to occupancy permits and certificates of occupancy; all warranties, guarantees and certificates required by the Principal have been complied with and supplied, including but not limited to operation and maintenance manuals; the Contractor has obtained and/or provided to the Principal; (i) written confirmation and approval from all relevant consultants and sub-contractors that the Stage have been correctly supplied, constructed, installed and commissioned in accordance with all requirements under the Contract and are operating and/or performing to specification; (ii) a list of all the items which the Contractor accepts to be Defects of the type referred to in paragraph (a) of this definition together with a proposed program for the rectification of such Defects; and all equipment has been supplied and installed and appropriate maintenance schedules have been established; |
| Preliminary Design | means the documents stated in Item 11; |
| Prescribed Notice | has the meaning in subclause 42.1; |
| Principal | means the Principal stated in Item 1; |
| Principal’s Project Requirements | means the Principal’s written requirements for the Works set out in Annexure Part F; |
| Program | the initial programs for each Stage set out in Annexure Part H: (a) as finalised (with the approval of the Superintendent) under clause 6.6 prior to Delivery Phase Approval; and (b) updated from time to time during the Delivery Phase in accordance with clause 32. |
| Progress Certificate | has the meaning in subclause 37.2; |
| Project Objectives | means the objectives set out in or reasonably to be inferred from the Principal's Project Requirements; |
| Provisional Allowance (Cost) | The work or goods so specified in Annexure Part A for which the sum of money specified in Annexure Part A is included in the Delivery Phase Price, as may be adjusted under subclause 6.5(a)(i)(A); |
| Provisional Allowance (Time) | The work or goods specified in the Contract Particulars for which the period of time specified in Annexure Part A is included in the Date for Completion, as may be adjusted under clause 6.6(a)(i)(A); |
| Public Liability Policy | has the meaning in clause 17; |
| Qualifying Cause of Delay | means: (a) any act, default or omission of the Superintendent, the Principal or its consultants, agents or other contractors (not being employed by the Contractor); (b) Inclement Weather; (c) Force Majeure; (d) a change in Legislative Requirements that meets the requirements of subclauses 11.2(a) and 11.2(b)(ii); or (d) any other cause that is expressly stated in the Contract to be a cause for an EOT; |
| Risk Reduction Input | All input into the Preliminary Design which a prudent, competent and experienced contractor (having been given the opportunity to undertake the Due Diligence which the Contractor has been given) would reasonably have provided to the Principal to ensure that all material risks that could be encountered during the Delivery Phase are identified and addressed during the Due Diligence Phase, including the presence of asbestos and any other hazardous materials at Site. |
| Schedule of Rates | means any schedule included in the Contract which, in respect of any section or item of Work to be carried out, shows the rate or respective rates of payment for the execution of that Work and which may also include lump sums, other sums, quantities and prices; |
| Security | means an approved unconditional undertaking (the form in Annexure Part B is approved) or an approved performance undertaking given by an approved financial institution or insurance company; |
| Site | means the lands and other places to be made available and any other lands and places made available to the Contractor by the Principal for the purpose of the Contract as set out in Annexure Part A; |
| Site Due Diligence | Means the Due Diligence of the Site set out in clause 6; |
| Stage | means a stage set out in Annexure Part A. |
| Subcontractor | in clauses 3 and 9 includes a Consultant; |
| Superintendent | means the person stated in Item 5 as the Superintendent or other person from time to time appointed in writing by the Principal to be the Superintendent and notified as such in writing to the Contractor by the Principal and, so far as concerns the functions exercisable by a Superintendent’s Representative, includes a Superintendent’s Representative; |
| Superintendent’s Representative | means an individual appointed in writing by the Superintendent under clause 21; |
| Temporary Works | means Work used in carrying out and completing WUC, but not forming part of the Works; |
| Test | has the meaning in subclause 30.1 and includes examine and measure; |
| the Works | means the whole of the Work to be carried out and completed in accordance with the Contract, including Variations provided for by the Contract, which by the Contract is to be handed over to the Principal; |
| Variation | has the meaning in clause 36; |
| WHS Law | means Work Health and Safety Act 2011 (Cth) and all Legislative Requirements dealing with or relevant to health and safety at work and of workers and others who may be affected by the carrying out of the WUC and includes any requirements of an authority exercising regulatory powers in respect of such matters; |
| WHS Regulations | means the Work Health and Safety Regulations 2011 (Cth); |
| Work | includes the provision of materials; |
| WUC (from ‘work under the Contract’) | means the Work which the Contractor is or may be required to carry out and complete under the Contract and includes variations, remedial Work, Construction Plant and Temporary Works, and like words have a corresponding meaning. |
|  | In the Contract: (a) references to days mean calendar days and references to a person include an individual, firm or a body, corporate or unincorporate; |
|  | (b) time for doing any act or thing under the Contract shall, if it ends on a Saturday, Sunday or Statutory or Public Holiday, be deemed to end on the day next following which is not a Saturday, Sunday or Statutory or Public Holiday; |
|  | (c) clause headings and subclause headings shall not form part of, nor be used in the interpretation of, the Contract; |
|  | (d) words in the singular include the plural and words in the plural include the singular, according to the requirements of the context. Words importing a gender include every gender; |
|  | (e) communications between the Principal, the Superintendent and the Contractor shall be in the English language; |
|  | (f) measurements of physical quantities shall be in legal units of measurement of the jurisdiction in Item 8; |
|  | (g) unless otherwise provided, prices are in the currency in Item 9(a); |
|  | (h) the law governing the Contract, its interpretation and construction, is the law of the jurisdiction in Item 8, and the parties submit to courts of that jurisdiction; and |
|  | (i) if pursuant to Annexure Part E to these General Conditions, clauses or their parts in these General Conditions are deleted, the Contract shall be read and construed as though the clause or its part has been deleted, whether or not that particular clause or its part has been struck from these General Conditions. |

Nature of Contract

Performance and payment

The Contractor shall carry out and complete WUC in accordance with the Contract and Directions authorised by the Contract.

Subject to the performance by the Contractor of its obligations under the Contract, the satisfaction of any conditions precedent to the Contractor’s right to receive payments, and the Principal’s rights under this Contract, the Principal shall pay the Contractor the Contract Sum adjusted by any additions or deductions made pursuant to the Contract, adjusted by any additions or deductions made pursuant to the Contract.

Contractor’s warranties

Without limiting the generality of subclause 2.1, the Contractor warrants to the Principal that:

the Contractor at all times shall be suitably qualified and experienced, and shall exercise due skill, care and diligence in the carrying out and completion of WUC;

the Contractor has examined the Preliminary Design and that such Preliminary Design is suitable, appropriate and adequate for the purpose stated in or reasonably to be inferred from the Contract (except to the extent set out in clause 6);

the Contractor shall carry out and complete the Contractor’s Design Obligations to accord with the Contract; and

the Contractor shall carry out and complete WUC in accordance with the Contract and Design Documents (for Construction) so that the Works, when completed, shall:

be fit for the purposes set out in, or reasonably to be inferred from, the Contract; and

comply with all the requirements of the Contract;

the Contractor shall undertake the Works in accordance with the Contract and Design Documents (for Construction):

using best work practices;

in a manner and to a quality commensurate with the purpose of the Works;

using materials of the nature described in the Contract, or failing any specific description then of the best quality available which are of merchantable quality and fit for their intended purposes;

the Works shall at all relevant times including when constructed, comply with all the requirements of:

the Contract and, in particular, requirements of the Principal at the Date of the Contract,

the requirements from time to time of the Building Code of Australia and all Legislative Requirements; and

all relevant authorities;

it shall supply and execute items not expressly mentioned in the Contract, but which are necessary for the satisfactory completion and performance of the Works, without:

adjustment to the Contract Sum;

the payment of any other extra remuneration to the Contractor, or

any EOT;

shall be solely responsible for the management, supply, installation, commissioning and completion of the Works in accordance with the provisions of this Contract;

shall ensure that each Stage progresses to Practical Completion in accordance with the Contract;

it is familiar with the conditions affecting the installation, commission and maintenance activities on and in the vicinity of the Site;

it has thoroughly inspected the Site;

it is completely satisfied as to its condition and that the Contract Sum is the maximum amount of money needed to complete all the Works including all foreseen and foreseeable risks, hazards and difficulties including, without limitation, adjacent properties to the site and public safety and including those risks that arose during Site Due Diligence under clause 6;

it shall furnish efficient business administration, supervision and an adequate supply of workers and materials and perform its obligations in the best way and in the most expeditious and economical manner consistent with the best interests of the Principal;

is responsible for the timely progression, evaluation and monitoring of the progress of the Works including, without limitation:

issues of supply, installation and commissioning;

the proper sequencing and timely management of all activities;

obtaining all necessary approvals and permits to be obtained from relevant authorities; and

is responsible for:

the collection (from the location nominated by the Superintendent), insurance, transport and installation of any materials supplied by the Principal; and

all other activities necessary for the completion of the Works including, without limitation, the engagement, supervision, control, coordination and direction of all Subcontractors and other resources and the supply of all necessary equipment and administrative requirements; and

subject to clause 9, the Consultants identified in the Contractor’s tender are suitably qualified and experienced.

Warranties unaffected

The warranties in subclause 2.2 and the Contractor's other warranties and obligations under the Contract and at law remain unaffected and the Contractor will bear and continue to bear full liability and responsibility in accordance with the Contract for the performance of WUC notwithstanding:

that the Preliminary Design has been carried out by or on behalf of the Principal and included in the Principal’s Project Requirements;

any receipt or review of, or comment or Direction on, Design Documents (for Construction) by the Superintendent; or

any Variation.

Not used

Not used

Not used

Not used

Security

Provision

Security shall be provided by the Contractor in accordance with Item 14.

Not used

No injunction

The Contractor must not take any steps, including the seeking of an injunction or other order of any court, to injunct or otherwise restrain:

the issuer of any Security from paying the Principal pursuant to that Security;

the Principal from taking any steps for the purpose of making a demand under any such Security or receiving payment under any such Security; or

the Principal using the money received under any Security.

Reduction and release

Upon the issue of the Certificate of Practical Completion in respect of a Stage, the Principal's entitlement to Security (other than in Item 14(e)) shall be reduced by the percentage or amount in Item 14(f) as applicable, and the reduction shall be released and returned within 14 days to the other party.

The Principal’s entitlement to Security in Item 14(e) shall cease 14 days after incorporation into the Works of the plant and materials for which that Security was provided.

The Principal's entitlement otherwise to Security shall cease 14 days after Final Certificate.

Upon a party’s entitlement to Security ceasing, that party shall release and return forthwith the Security to the other party.

Trusts and interest

Except where held by a government department or agency or a municipal, public or statutory authority, any portion of Security (and interest earned thereon) which is cash, shall be held in trust for the party providing them until the Principal or the Contractor is entitled to receive them.

Interest earned on Security not required to be held in trust shall belong to the party holding that Security.

Replacement of Security

If:

the Contract Sum (Stage) is increased by more than 10% due to a Variation, the Contractor must within 14 days of a request to do so by the Principal provide a replacement Security; or

otherwise the Security provided is due to expire,

- the Contractor must provide a replacement Security no later than 28 days prior to the date the Security expires, for the period of 1 year from the expiry of the replaced Security.

Deed of guarantee, undertaking and substitution

Where:

a party is a related or subsidiary corporation (as defined in the applicable corporations law of the jurisdiction); and

a form of Deed of Guarantee, Undertaking and Substitution was included in the tender documents,

that party shall, within 14 days after receiving a written request from the other party, provide such Deed of Guarantee, Undertaking and Substitution duly executed and enforceable.

Due Diligence Phase

Proactive Review of Preliminary Design and Site

The Contractor acknowledges that:

the Principal provided the Contractor with the Preliminary Design for each Stage prior to the Date of the Contract; and

the Principal will provide the Contractor with access to the Site for each Stage for the purposes of Due Diligence in accordance with subclause 6.8.

The Contractor must undertake a proactive and comprehensive due diligence of each Preliminary Design and each Site by physically inspecting each Site to:

ensure that each Preliminary Design is free from Buildability Issues and for that purpose identify and propose all relevant Buildability Input in accordance with subclause 6.2;

identify and propose all relevant Innovation Input and Risk Reduction Input in accordance with subclauses 6.5 and 6.6; and

review, discuss and agree all input proposed under subparagraphs (i) and (ii) with the Superintendent provided that, if the Contractor is unable to obtain the Superintendent’s agreement to any Due Diligence Input, then the Superintendent may give the Contractor a Direction as to how the Due Diligence Input will be resolved.

Buildability Input

Without limiting paragraph (b), but for the purposes of paragraph (b)(i), the Contractor must:

promptly (and in any event within 2 business days) after having been given access to each Site, commence the Due Diligence;

if any Preliminary Design contains any Buildability Issues, provide the Principal (in the draft Due Diligence Report under clause 6.3(a)(i)) with all comments, advice and other assistance necessary and appropriate to enable the Superintendent to consider how the relevant Preliminary Design should be finalised so that the Buildability Issues are fully addressed ("Buildability Input");

without limiting subparagraph (ii), provide the Superintendent with detailed advice as to the actions required to finalise the relevant Buildability Input so that:

all Buildability Issues are fully addressed; and

all Buildability Input is provided, considered and (if applicable) incorporated in the relevant final Due Diligence Report,

- at a rate of progress so that the Contractor can comply with its obligations under the Contract and each Delivery Phase Approval can be achieved by each Date for Delivery Phase Approval;

if the Contractor requires any information, guidance, or other Direction from the Superintendent for the purpose of finalising the relevant Due Diligence Report, promptly request the information, guidance or Direction from the Superintendent;

proactively program and manage the Due Diligence Activities and finalisation of the relevant Due Diligence Report so as to ensure that there are no delays to achieving each Delivery Phase Completion or each Practical Completion of the Works and that value for money for the Principal is otherwise maximised; and

otherwise do all things necessary to ensure that each Preliminary Design is free from Buildability Issues and each final Due Diligence Report incorporates all required Buildability Input.

The Contractor:

unequivocally accepts responsibility for all work, cost, delay and disruption arising out of or in connection with Buildability Issues; and

agrees that the Principal will not be liable upon any Claim (to the extent permitted by law) arising out of or in connection with Buildability Issues, all of which the Contractor will be deemed to have fully allowed for in the Contract Sum.

Without limiting paragraph (b), the Contractor acknowledges that in the Delivery Phase:

the Superintendent may give the Contractor a Direction as to how to overcome a Buildability Issue, including relevant design details showing any changes to the workmanship or materials to be used to complete the Works; and

the Contractor will, to the extent permitted by law, have no Claim against the Principal arising out of or in any way in connection with:

the Buildability Issue;

the Superintendent's Direction; or

any work, cost, delay or disruption arising out of or in any way in connection with the Superintendent's Direction.

Due Diligence Report

The Contractor must:

within 14 days of being provided access to each Site - submit a draft Due Diligence Report to the Superintendent, containing all proposed Due Diligence Input;

within 7 days of being given a direction by the Superintendent under paragraph (b)(iii) agreeing to, or otherwise stating how to resolve, any Due Diligence Input - submit a revised draft Due Diligence Report to the Superintendent; and

no later than 7 days before each Date for Delivery Phase Approval - submit the final draft Due Diligence Report to the Superintendent.

If the first draft Due Diligence Report is approved by the Superintendent, then the Superintendent will issue a written notice to the Contractor.

Risk of Buildability Issues

No representation has been, is or will be deemed to be, made to the Contractor by the Principal, the Superintendent or any of their employees, agents or consultants about the accuracy, completeness or sufficiency of the Preliminary Design or that it represents a completed design of the Works which:

is suitable for construction purposes; or

is free from Buildability Issues.

The Principal has not assumed, nor does it assume, a duty of care to the Contractor concerning the Preliminary Design or any Buildability Issues.

The risk of:

            - Buildability Issues; and

any delay, disruption, cost, loss or damages suffered or incurred as a result of Buildability Issues,

- is assumed by the Contractor.

The Contractor warrants that:

            - in preparing and submitting each Due Diligence Phase Fee and each Delivery Phase Price it has provided sufficient resources to:

undertake the Due Diligence; and

provide the Superintendent with all Buildability Input and other assistance necessary to enable each Due Diligence Report to be finalised so that it captures all Buildability Issues required to enable the Contractor to finalise each Preliminary Design in the Delivery Phase so that it is free from Buildability Issues;

the Delivery Phase Price covers, in addition to the Contractor's other obligations under the Contract, the assumption of the risks described in this subclause 6.4 including the requirement to perform all WUC arising out of or in any way in connection with overcoming all Buildability Issues; and

without limiting paragraph (c), all work which it is required to carry out arising out of or in connection with overcoming Buildability Issues will be deemed to be part of the WUC, even if the work is not contained, described or referred to (either expressly or impliedly) in the Preliminary Design.

Cost Planning

The Contractor must review the Cost Plan for each Stage, as it undertakes the Due Diligence and prepares the relevant draft Due Diligence Report, and:

ensure that the cost of construction of the Works as designed having regard to each Preliminary Design and each Site:

is in accordance with each Cost Plan and in any event does not exceed each Delivery Phase Price, except to the extent that it demonstrates in the relevant Cost Plan to the satisfaction of the Superintendent (acting reasonably) that an adjustment is required in a Provisional Allowance (Cost); and

fully takes into account all Project Objectives;

provide proactive and innovative recommendations to the Superintendent (as part of its Innovation Input) as to how each Preliminary Design should be modified to ensure that:

the cost of the construction of the Works as designed is in accordance with each Cost Plan and does not in any event exceed the relevant Delivery Phase Price as a result of a proposed adjustment to a Provisional Allowance (Cost) referred to in paragraph (a)(i)(A); and

the Project Objectives are maximised,

- as a result of any Due Diligence Input identified in its relevant draft Due Diligence Report without affecting compliance with the relevant Preliminary Design (other than Buildability Issues) and the other requirements of the Contract;

provide proactive and innovative recommendations to the Superintendent (as part of its Risk Reduction Input) as to any risk reduction studies the Contractor considers should be conducted at the Site, to ensure that:

the cost of the construction of the Works as designed is in accordance with each Cost Plan and does not in any event exceed the relevant Delivery Phase Price as a result of a proposed adjustment to a Provisional Allowance (Cost) referred to in paragraph (a)(i)(A); and

the Project Objectives are maximised,

- as a result of any risks identified in the relevant draft Due Diligence Report without affecting compliance with the relevant Preliminary Design (other than Buildability Issues) and the other requirements of the Contract;

review, discuss and agree (subject to clause 6.1(b)(iii)) all Innovation Input and Risk Reduction Input with the Superintendent;

if required by the Superintendent under subparagraph [(iv)], undertake any risk reduction studies on terms agreed by the Superintendent; and

update each Cost Plan to ensure that it accurately reflect the requirements of subparagraph (i) and the Innovation Input provided under subparagraph (ii) and agreed to be implemented under subparagraph (iv) and the outcome of any risk reduction studies undertaken under subparagraph (v).

The Contractor must:

submit updated Cost Plans under subparagraph (a)(v) to the Superintendent;

revise each Cost Plan submitted under subparagraph (i) in accordance with the Superintendent's directions; and

obtain the Superintendent's approval to each updated Cost Plan as a condition precedent to payment of the relevant Due Diligence Fee.

Each draft of each Cost Plan to be prepared under paragraph (b) must include:

identification in detail of all work required for, and all risks which could be encountered in, Practical Completion of the Works, which a prudent, competent and experienced contractor would anticipate and provide for in its cost plan for the WUC;

a cost analysis of each component of the Works, including a detailed break-up by reference to each trade package and other component (including self-performed work, on site overhead, off-site overhead, profit and contingency on a fully open book basis, identified as a separate line item in each draft Cost Plan;

all proposed changes to any draft Cost Plan and any Delivery Phase Price (if any) arising out of any Buildability Issues and all available measures for proactively avoiding or mitigating the effect of the Buildability Issues (including all Innovation Input under paragraph (a)(ii) and the outcomes of any Risk Reduction Input under paragraph (a)(v)), provided that no proposed Delivery Phase Price can be greater than the relevant initial  Delivery Phase Price (without the prior written approval of the Superintendent before the submission of each draft Cost Plan); and

all such other matters as the Superintendent may require in writing.

The Contractor must, if a draft Cost Plan submitted by the Contractor are rejected by the Superintendent (in the Superintendent's absolute discretion), submit an amended Cost Plan.

If the relevant Cost Plan is approved by the Superintendent, then the Superintendent will issue a written notice to the Contractor.

Programming

The Contractor must review each Program, as it undertakes the Due Diligence and prepares the relevant draft Due Diligence Report, and:

ensure that the duration for the construction of the Works as designed having regard to each Preliminary Design and each Site:

does not exceed the Date for Practical Completion, except to the extent that it demonstrates in the relevant Program to the satisfaction of the Superintendent (acting reasonably) that an adjustment is required in a Provisional Allowance (Time);

complies with the Master Program; and

fully takes into account all Project Objectives;

provide proactive and innovative recommendations to the Superintendent (as part of its Innovation Input) as to how the design of the Works should be modified to ensure that:

the duration of the construction of the Works as designed does not exceed any Date for Practical Completion as a result of a proposed adjustment to a Provisional Allowance (Time) referred to in paragraph (a)(i)(A); and

the Project Objectives are maximised,

- as a result of any Due Diligence Input identified in the relevant Due Diligence Report without affecting compliance with the relevant Preliminary Design (other than Buildability Issues) and the other requirements of the Contract;

provide proactive and innovative recommendations to the Superintendent (as part of its Risk Reduction Input) as to any risk reduction studies the Contractor considers should be conducted at the Site, to ensure that:

the duration of the construction of the Works as designed does not exceed any Date for Practical Completion as a result of a proposed adjustment to a Provisional Allowance (Time) referred to in paragraph (a)(i)(A); and

the Project Objectives are maximised,

- as a result of any risks identified in each draft Due Diligence Report without affecting compliance with the relevant Preliminary Design (other than Buildability Issues) and the other requirements of the Contract;

review, discuss and agree (subject to clause 6.1(b)(iii)) all Innovation Input and Risk Reduction Input with the Superintendent;

if required by the Superintendent under subparagraph (iv), undertake any risk reduction studies on terms agreed by the Superintendent; and

update each Program to ensure that it accurately reflects the requirements of subparagraph (i) and the Innovation Input provided under subparagraph (ii) and agreed to be implemented under subparagraph (iv) and the outcomes of any risk reduction studies undertaken under subparagraph (v).

The Contractor must:

submit updated Programs under subparagraph (a)(iv) to the Superintendent;

revise each Program submitted under subparagraph (i) in accordance with the Superintendent's directions; and

obtain the Superintendent's approval to each updated Program as a condition precedent to payment of the Due Diligence Fee.

Each draft of each Program to be prepared under subparagraph (b)(ii) must:

include identification in detail of all work required for, and all risks which could be encountered in, Completion of the Works, which a prudent competent and experienced contractor would anticipate and provide for in its program for the WUC;

comply with the Master Program;

include a detailed recommendation as to every reasonably possible dates which the Principal could set as Dates for Practical Completion for the Works;

have regard to all relevant considerations including:

the desirability of staging and sequencing the Works; and

the paramount importance to the Principal of balancing between minimising the time to achieve Completion of the Works (on the one hand) and maximising time certainty for the Principal (on the other hand);

all proposed changes to each draft Program and each Date for Practical Completion (if any) arising out of any Buildability Issues and all available measures for proactively avoiding or mitigating the effect of the Buildability Issues (including all Innovation Input under paragraph (a)(ii) and the outcomes of any Risk Reduction Input undertaken under subparagraph (a)(v)), provided that no proposed date for completion can be after the relevant Date for Practical Completion (without the prior written approval of the Superintendent before the submission of the relevant draft Program); and

include all such other matters as the Superintendent may require in writing.

The Contractor must:

if a draft Program submitted by the Contractor under paragraph (b) is rejected by the Superintendent (in the Superintendent's absolute discretion), submit an amended Program (within the time required by the Superintendent);

in the process of preparing every Program, co-operate with the Principal, the Superintendent and all other people nominated by the Superintendent for the purpose of furthering the considerations referred to in subparagraph (c)(iv); and

ensure that no proposed Date for Practical Completion in a draft Program exceeds the relevant initial Date for Practical Completion (without the prior written approval of the Superintendent before the submission of the draft Program).

If the Program is approved by the Superintendent, then the Superintendent will issue a written notice to the Contractor.

Other Due Diligence Phase Obligations

In addition to the Contractor's obligations under this clause 6, the Contractor must do all such things or tasks as may be necessary to achieve each Delivery Phase Approval, including to provide the Superintendent with such assistance, provide such documents and attend such meetings as the Superintendent may require in writing for the purpose of obtaining each Delivery Phase Approval.

Site Access During the Due Diligence Phase

The Principal will use its reasonable endeavours to provide the Contractor with such access to each Site during the Due Diligence Phase as may be reasonably necessary for the carrying out of the relevant Due Diligence.

The Contractor acknowledges and agrees that, without limiting paragraph (a), Site access during the Due Diligence Phase will be contingent upon:

the Principal having a right of access to the relevant Site;

evidence satisfactory to the Contract Administrator under subclause 19.1 that the Contractor has caused to be effected and maintained or otherwise have the benefit of the insurances required under the Contract;

the Contractor having submitted a request in writing to the Superintendent during the Due Diligence Phase for access to the Site setting out:

the areas of the proposed access;

the timing of the proposed access;

the reasons why the proposed access is necessary to enable the Contractor to commence and progress the Due Diligence Activities; and

the mitigation measures that the Contractor proposes to put in place to avoid any disruption or inconvenience that may be caused to the Principal, other contractors, residents and any other person authorised by the Principal or the Superintendent to occupy, use, operate, maintain or access the Site if the Contractor is given the proposed access; and

the Contractor's request being approved by the Superintendent in writing.

Negotiations Prior to Delivery Phase Approval

Prior to each Date for Delivery Phase Approval, and by no later than the date specified by the Superintendent, the Contractor must:

notify the Superintendent and the Principal of its proposed adjustment (if any) required to:

the relevant date for commencement of Works on Site;

the Preliminary Design to constitute the Design Documents (For Construction), having regard to the Contractor's obligations between subclauses 6.1 and 6.4;

the relevant Provisional Allowance (Cost) of the relevant Delivery Phase Price; and

the relevant Date for Practical Completion,

- arising as a result of design development, cost planning and programming carried out during the relevant Due Diligence Phase including having regard to the Contractor’s obligations under this clause 6; and

thereafter undertake genuine and good faith negotiations with the Principal to reach agreement, in the Principal’s absolute discretion, as to such adjustments (if any).

As part of the process of undertaking negotiations with the Principal, the Contractor must provide such documents and information as the Superintendent may require including:

a detailed breakdown of cost in respect of each Delivery Phase Price on a fully open book basis; and

evidence of pricing from proposed subcontractors and suppliers.

If agreement on all of the matters in paragraph (a) is reached by each Date for Delivery Phase Approval, then:

the Principal will record that agreement in writing by way of formal amendment to the Annexure Part A and (if applicable) the other documents forming part of the Contract; and

the Contractor must execute the amendment referred to in subparagraph (i) on the date required by the Principal, provided that such amendment is subject to, and will only take effect upon, execution by the Principal and the relevant Delivery Phase Approval being achieved in accordance with clause 6.10.

Delivery Phase Approval

The Principal must:

If a Delivery Phase Approval is achieved:

issue a written notice to the Contractor stating that Delivery Phase Approval is achieved; and

execute the amendment referred to in subclause 6.9(c) on the same date that the notice is issued under sub subparagraph A; and

if the relevant Delivery Phase Approval has not been achieved, issue a written notice so advising the Contractor, in which case subclause 6.11 will apply.

If the Principal issues a notice under subparagraph (a)(i)A, then:

the Contractor must:

immediately commence to carry out the remainder of the WUC including to complete the design of and construct, commission, complete and handover the Works in accordance with the terms of the Contract (as amended in accordance with subclause 6.9(c); and

unless otherwise stated, carry out the WUC at its cost; and

the Principal must give the Contractor sufficient access to the relevant Site to allow it to commence work on Site in accordance with subclause 24.1.

Phased Engagement

The Contractor acknowledges and agrees that:

the Principal may, in its absolute discretion, issue a notice under clause 6.10(a)(ii) if a Delivery Phase Approval has not been achieved by the relevant Date for Delivery Phase Approval;

it will have no entitlement to complete design of or construct, commission, complete and handover any part of the Works during the relevant Delivery Phase unless the Principal issues a notice under subclause 6.10(a)(i)A; and

the splitting of the WUC into the Due Diligence Phase and the Delivery Phase is solely for the benefit of the Principal including, without limiting the other elements required to achieve each Delivery Phase Approval, to:

enable the Contractor to undertake the Due Diligence;

enable the Principal to be satisfied (in its absolute discretion) that it will maximise value for money for the Principal to have the Contractor proceed with the relevant Delivery Phase;

give the Principal an opportunity to elect (in its absolute discretion) not to proceed with the Contractor from the relevant Due Diligence Phase to the relevant Delivery Phase; and

to reach agreement in relation to the matters contemplated in subclause 6.9 (in its absolute discretion),

- and the rights and obligations of the parties and the functions of the Superintendent are to be construed accordingly.

The Principal may, in the Principal’s absolute discretion, at any time and from time to time, by written notice to the Contractor unilaterally extend the relevant Date for Delivery Phase Approval.

Neither an extension under paragraph (b), nor the issue of a notice under subclause 6.10(a)(ii) will:

limit or affect the Contractor's obligations or liabilities under this Contract or prejudice the right of the Principal to exercise any right or remedy (including recovery of damages, whether while electing to keep the Contract on foot or after termination) which it may have where the Contractor breaches the Contract, whether under the Contract or otherwise according to law; or

entitle the Contractor to bring a Claim against the Principal.

The Contractor acknowledges that any act or omission of the Principal, which prevents a Delivery Phase Approval being achieved by the relevant Date for Delivery Phase Approval, will not:

entitle the Contractor to bring a claim against the Principal; or

limit or affect any right of the Principal or the Superintendent, including the right of the Principal to elect not to proceed with the Contractor to deliver the Works or to issue a notice under subclause 6.10(a)(ii),

- whether on the basis that the obligation to finalise, agree, achieve or obtain the relevant matter has become an obligation to finalise, agree, achieve or obtain the relevant matter within a reasonable time or on any other basis at law or in equity.

The Contractor acknowledges that:

an absolute discretion in the Superintendent or the Principal under this clause 6 is not required to be exercised for the benefit of the Contractor; and

the exercise or failure to exercise such an absolute discretion is not capable of being the subject of a dispute or difference for the purpose of clause 43 or otherwise subject to review.

Failure to Achieve Delivery Phase Approval

If the Principal issues a notice under clause 6.10(a)(ii), then:

the Contractor will:

have no entitlement to design, commence, construct, commission, complete or handover any part of the Works;

be entitled to payment of the relevant Due Diligence Phase Price due and payable for the WUC completed in accordance with the Contract before issue of the relevant notice; and

not be entitled to payment of any portion of the relevant Delivery Phase Price or to make any Claim (to the extent permitted by law) against the Principal arising out of, or in any way in connection with, the relevant notice, this Contract, the WUC or the Works other than for the amount payable under subparagraph (ii);

subject to paragraph (c), the Contractor must:

comply with subclause 8.5, including by handing over to the Superintendent copies (or, where required by the Superintendent, originals) of all Contract Documents prepared by the Contractor to the date of issue of the relevant notice (whether complete or not);

immediately take all steps necessary to novate to the Principal (or its nominee) any of the subcontractors required by the Superintendent to be novated; and

co-operate with the Principal and any third parties required by the Superintendent, including the Host Nation, and take all other steps necessary, to ensure that the Principal is able to re-tender or procure the execution of the Works under paragraph (c)(i).

the Principal may:

re-tender the execution of the Works (whether with or without obtaining a tender from the Contractor) or procure the execution of the Works in any other manner which the Principal may determine; and

without limiting the licence granted under subclause 10.2, use the Contract Documents for the purposes of re-tendering or procuring the execution of the Works under subparagraph (i).

Service of notices

General

A notice, demand, certification, process or other communication relating to the Contract must be in writing in English and may be given by an agent of the sender and must be delivered by email.

Notices by email

Subject to subclause 7.3, notice is given by email at the earlier of:

    - delivery to the email address to which it was sent; or

one hour after the email enters the server of the email address to which it was sent, provided that no delivery or transmission error is received by the sender within one hour of the time of sending shown on the "sent" email.

After hours notices

If a notice is given:

after 5.00 pm in the place of receipt; or

on a day which is not a business day in the place of receipt,

it is taken as having been given on the next business day.

Contract documents

Discrepancies

The order of precedence of the Contract Documents is as set out in article 3 of the Formal Instrument of Agreement, except that in the event of any ambiguity, discrepancy or inconsistency in or between any specification or technical document comprising the Contract:

figured shall prevail over scaled dimensions in a discrepancy; and

the higher standard of quality or quantum will prevail as directed by the Superintendent.

- Otherwise, if either party discovers any inconsistency, ambiguity or discrepancy in any document prepared for the purpose of carrying out WUC, that party shall give the Superintendent written notice of it. The Superintendent, thereupon, and upon otherwise becoming aware, shall direct the Contractor as to the interpretation and construction to be followed.

The Contractor shall bear the cost of compliance with a Direction under this subclause and will not be entitled to make any Claim against the Principal arising out of or in connection with the Direction or the inconsistency, ambiguity or discrepancy.

Principal-supplied documents

The Principal shall supply to the Contractor the documents and number of copies thereof, both stated in Item 16.

They shall:

remain the Principal’s property and be returned to the Principal on written demand; and

not be used, copied nor reproduced for any purpose other than WUC.

Contractor-supplied documents and design review

The Contractor shall submit to the Superintendent the documents and number of copies at the times or stages stated in Item 17.

Other documents and information required by the Contract, unless elsewhere stated in the Contract, shall be submitted not less than 14 days before the Work described in the documents is commenced and shall be in a form satisfactory to the Superintendent.

The Superintendent may:

review any submitted draft Design Documents (For Construction), or any resubmitted draft Design Documents (for Construction), prepared and supplied by the Contractor; and

within the number of days specified in Item 18 of the submission by the Contractor of such draft Design Documents (for Construction) or resubmitted draft Design Documents (for Construction), reject the draft Design Documents (for Construction) if in the Superintendent's reasonable opinion, the draft Design Documents (for Construction) do not comply with the requirements of the Contract.

- If any draft Design Documents (for Construction) are rejected, the Contractor must submit amended draft Design Documents (for Construction) to the Superintendent.

- The Contractor must not commence construction of any part of the Works to which any draft Design Documents (for Construction) it has submitted to the Superintendent applies, unless the Superintendent has had the number of days specified in the Item 18 to review the draft Design Documents (for Construction) and has not rejected the draft Design Documents (for Construction).

If the Contractor submits a document to the Superintendent, then:

the Superintendent shall not be required to check that document for errors, omissions, inconsistencies, ambiguities, discrepancies or compliance with the Contract; and

notwithstanding subclause 2.1, any Superintendent's acknowledgment or approval shall not prejudice the Contractor’s obligations;

Copies of documents supplied by the Contractor shall be the Principal’s property but shall not be used nor copied otherwise than for the use, repair, maintenance or alteration of the Works.

Availability

The Contractor shall keep available to the Superintendent and the Principal:

on Site, one complete set of documents affecting WUC and supplied by a party or the Superintendent; and

at the place of manufacture or assembly of any significant part of WUC off Site, a set of the documents affecting that part.

Confidential information

The parties shall ensure that there are kept confidential such documents, samples, models, patterns and other information as are supplied and clearly identified as confidential or that a party, acting reasonably, would assume to be confidential.

If required in writing by a party, the other party shall enter into a separate agreement not to disclose to anyone else any confidential matter even after Final Certificate or earlier termination of the Contract.

The Contractor acknowledges that nothing in this clause prevents the Principal from disclosing confidential information where the disclosure:

is disclosed by the Principal to its personnel solely in order to comply with its obligations, or to exercise its rights, under this Contract;

is disclosed to the Principal’s internal management personnel, solely to enable effective management or auditing of Contract-related activities;

is disclosed by the Principal to the responsible Minister;

is disclosed by the Principal in response to a request by a House or a Committee of the Parliament of the Commonwealth of Australia;

is shared by the Principal within the Principal's organisation, or with another agency, where this serves the Commonwealth’s legitimate interests;

is authorised or required by law to be disclosed; or

is in the public domain otherwise than due to a breach of this subclause 8.5.

Where the Principal discloses confidential information to another person pursuant to subclauses 8.5(a) to 8.5(e), the Principal will notify the receiving person that the information is confidential.

In the circumstances referred to in subclauses 8.5(a), 8.5(b) and 8.5(e) the Principal agrees not to provide the information unless the receiving person agrees to keep the information confidential.

*

Media

The Contractor shall not disclose any information concerning the project for distribution through any communications media without the Principal’s prior written approval (which shall not be unreasonably withheld). The Contractor shall refer to the Principal any enquiries from any media concerning the project.

Assignment and subcontracting

Assignment

Neither party shall, without the other’s prior written approval (including terms) assign the Contract or any payment or any other right, benefit or interest thereunder.

Subcontracting generally

The Contractor shall engage and retain the consultants identified in the Contractor’s tender. The Contractor shall not without the Superintendent's prior written approval (which shall not be unreasonably withheld) allow a Subcontractor to assign a subcontract or any payment or any other right, benefit or interest thereunder.

With a request for approval, the Contractor shall give the Superintendent written particulars of the Work to be subcontracted and the name and address of the proposed Subcontractor. The Contractor shall give the Superintendent other information which the Superintendent reasonably requests, including the proposed subcontract documents without prices.

Within 14 days of the Contractor’s request for approval, the Superintendent shall give the Contractor written notice of approval or of the reasons why approval is not given.

The Superintendent may give approval under this clause on such reasonable conditions as the Superintendent considers appropriate or necessary, including, without limiting the generality of the above, a condition that any subcontract include one or more of the following:

          - provision that the Subcontractor shall not assign nor subcontract without the Contractor’s written consent;

provisions which may be reasonably necessary to enable the Contractor to fulfil the Contractor’s obligations to the Principal; and

provision that if the Contract is terminated and upon the Subcontractor being paid the sum certified by the Superintendent as owing to the Subcontractor, the Contractor and the Subcontractor shall, after the Principal has done so, promptly execute a deed of novation in the form of Annexure Part C.

- For the purpose of effecting such novation only, the Contractor hereby irrevocably appoints the Superintendent to be the Contractor’s attorney with authority to execute such documents as are necessary to give effect to the novation and to bind the Contractor accordingly and, where the Subcontractor is a consultant, provision that the Subcontractor shall effect and maintain professional indemnity insurance on the same terms as are required under Items 24(c) and 24(d).

Not used

Not used

Contractor’s responsibility

Except where the Contract otherwise provides, the Contractor shall be liable to the Principal for the acts, defaults and omissions of Subcontractors and employees and agents of Subcontractors as if they were those of the Contractor.

Approval to subcontract shall not relieve the Contractor from any liability or obligation under the Contract.

Intellectual property rights

Warranties and indemnities

The Principal warrants that, unless otherwise provided in the Contract, the Principal’s Project Requirements, design, materials, documents and methods of working, each specified in the Contract or provided or directed by the Principal or the Superintendent shall not infringe any Intellectual Property Right.

The Contractor warrants that any other design, materials, documents and methods of working, each provided by the Contractor, shall not infringe any Intellectual Property Right.

Each party shall indemnify the other against such respective infringements.

All intellectual property in all design and documents developed by the Contractor as part of the WUC vest in the Principal.

Intellectual property rights granted to Principal

Copyright and property in the draft Design Documents (for Construction) hereby vest in the Principal, and the Principal grants to the Contractor an irrevocable licence to use the draft Design Documents (for Construction) for WUC.

The Contractor shall do everything necessary to perfect such vesting.

The Contractor shall ensure that the draft Design Documents (for Construction) are used, copied and supplied only for the purpose of WUC.

Legislative requirements

Compliance

The Contractor shall satisfy all Legislative Requirements except those in Item 22(a) or directed by the Superintendent to be satisfied by or on behalf of the Principal.

The Contractor, upon finding that a Legislative Requirement is at variance with the Contract, shall promptly give the Superintendent written notice thereof.

Changes

If a Legislative Requirement comes into force after the Date of the Contract, the party discovering the Legislative Requirement must promptly give the Superintendent and the other party notice in writing.

If the Legislative Requirement:

necessitates a change:

to the Works;

to so much of WUC as is identified in Item 22(b); and

being the provision of services by a municipal, public or other statutory authority in connection with WUC;

could not reasonably have been anticipated by the Contractor acting reasonably and exercising due diligence at the Date of the Contract; and

causes the Contractor to incur more or less cost than otherwise would have been incurred after the giving of the notice under paragraph (a) which arise directly from the Legislative Requirement, as determined by the Superintendent,

- the difference shall be assessed by the Superintendent and added to or deducted from the Contract Sum.

Notification

The Contractor must immediately notify the Superintendent and the Principal in writing if:

it breaches any Legislative Requirement or fails to comply with subclause 11.1; or

it receives any certificates or other documents in connection with the Contractor's compliance or otherwise with any Legislative Requirement or any environmental or occupational health and safety matter in relation to the Works including any licence, consent, approval, notice, policy, procedure or practice.

Australian Standards

Unless otherwise provided in the Contract, the Contractor must ensure that (in the absence of any express contractual provision or Legislative Requirement to the contrary) the Works comply with all relevant Australian Standards.

Protection of people and property

The Contractor shall:

take measures necessary to protect people and property;

avoid unnecessary interference with the passage of people and vehicles; and

prevent nuisance and unreasonable noise and disturbance.

If the Contractor damages property, the Contractor shall promptly rectify the damage and pay any compensation which the law requires the Contractor to pay.

If the Contractor fails to comply with an obligation under this clause, the Principal, after the Superintendent has given reasonable written notice to the Contractor and in addition to the Principal’s other rights and remedies, may have the obligation performed by others. The cost thereby incurred shall be certified by the Superintendent as moneys due from the Contractor to the Principal.

Urgent protection

If urgent action is necessary to protect WUC, other property or people and the Contractor fails to take the action, in addition to any other remedies of the Principal, the Superintendent may take the necessary action. If the action was action which the Contractor should have taken at the Contractor’s cost, the Superintendent shall certify the cost incurred as moneys due from the Contractor to the Principal.

If time permits, the Superintendent shall give the Contractor prior written notice of the intention to take action pursuant to this clause.

Care of the work and reinstatement of damage

Care of WUC

Except as provided in subclause 14.3, the Contractor shall be responsible for the care of, in respect of a Stage:

the whole of the WUC comprising the Stage from and including the date of commencement of WUC to 4:00 pm on the relevant Date of Practical Completion, at which time responsibility for the care of the Stage (except to the extent provided in paragraph (b)) shall pass to the Principal; and

outstanding Work and items to be removed from the Site by the Contractor after 4:00 pm on the relevant Date of Practical Completion until completion of outstanding Work or compliance with clauses 29, 30 and 35.

Without limiting the generality of paragraph (a), the Contractor shall be responsible for the care of unfixed items accounted for in a Progress Certificate and the care and preservation of things entrusted to the relevant Contractor by the Principal or brought onto the Site by Subcontractors for carrying out the relevant WUC.

Reinstatement

If loss or damage, other than that caused by an Excepted Risk, occurs to WUC during the period of the Contractor’s care, the Contractor shall at its cost, rectify such loss or damage.

In the event of loss or damage being caused by any of the Excepted Risk (whether or not in combination with other risks), the Contractor shall to the extent directed by the Superintendent, rectify the loss or damage and such rectification shall be a deemed Variation. If loss or damage is caused by a combination of Excepted Risks and other risks, the Superintendent in pricing the Variation shall assess the proportional responsibility of the parties.

Excepted risks

The Excepted Risks causing loss or damage, for which the Principal is liable, are:

war, invasion, acts of foreign enemies, hostilities (whether war be declared or not), civil war, rebellion, revolution, insurrection or military or usurped power, martial law or confiscation by order of any government or public authority; and

ionising radiations or contamination by radioactivity from any nuclear fuel or from any nuclear waste from the combustion of nuclear fuel not caused by the Contractor or its Subcontractors or either’s employees or agents.

Damage to persons and property other than WUC

Indemnity by Contractor

Insofar as this subclause applies to property, it applies to property other than WUC.

The Contractor shall indemnify the Principal against:

loss of or damage to the Principal’s property; and

Claims in respect of personal injury or death or loss of, or damage to, any other property,

arising out of or as a consequence of the carrying out of WUC, but the indemnity shall be reduced proportionally to the extent that the act or omission of the Superintendent, the Principal or its consultants, agents or other contractors (not being employed by the Contractor) may have contributed to the injury, death, loss or damage.

This subclause shall not apply to:

the extent that the Contractor’s liability is limited by another provision of the Contract;

exclude any other right of the Principal to be indemnified by the Contractor;

things for the care of which the Contractor is responsible under subclause 14.1; and

Claims in respect of the Principal’s right to have WUC carried out.

Survival of indemnity

The indemnity in subclause 15.1 will survive the termination of the Contract.

- 16A   Insurance of the Works

Before commencing WUC, the Contractor shall insure all the things referred to in subclause 14.1 against loss or damage resulting from any cause until the Contractor ceases to be responsible for their care.

Without limiting the generality of the obligation to insure, such insurance shall cover the Contractor’s liability under subclause 14.2 and things in storage off Site and in transit to the Site but may exclude:

the cost of making good fair wear and tear or gradual deterioration, but shall not exclude the loss or damage resulting therefrom;

the cost of making good faulty design, workmanship and materials, but shall not exclude the loss or damage resulting therefrom;

consequential loss of any kind, but shall not exclude loss of or damage to the Works;

damages for delay in completing or for the failure to complete the Works;

loss or damage resulting from ionising radiations or contamination by radioactivity from any nuclear fuel or from any nuclear waste from the combustion of nuclear fuel resulting from any cause;

          - loss or damage resulting from the Excepted Risks referred to in paragraphs (c) and (d) of subclause 14.3.

The insurance cover shall be for an amount not less than the aggregate of the:

          - Contract Sum (Aggregate); and

provision in Item 23(a) to provide for costs of demolition and removal of debris.

Insurance shall be in the joint names of the parties, shall cover the parties, Consultants and Subcontractors whenever engaged in WUC for their respective rights, interests and liabilities and, except where the Contract otherwise provides, shall be with an insurer and in terms both approved in writing by the Principal (which approvals shall not be unreasonably withheld).

The insurance shall be maintained until the Contractor ceases to be responsible under subclause 14.1 for the care of anything.

- 16B   Professional indemnity insurance

Before commencing WUC, the Contractor shall effect and maintain professional indemnity insurance with levels of cover not less than stated in Item 24(a).

The insurance shall be maintained until the Final Certificate is issued after the expiry of the final Defects Liability Period and thereafter for the period as stated in Item 24(b).

The Contractor shall ensure that every Consultant, if within a category stated in Item 24(c), shall effect and maintain professional indemnity insurance with levels of cover not less than stated in Item 24(c) applicable to that category.

Each such Consultant’s professional indemnity insurance shall be maintained until the Final Certificate is issued after the expiry of the final Defects Liability Period and thereafter for the period as stated in Item 24(d).

- Public liability insurance

Before commencing WUC, the Contractor shall effect and maintain for the duration of the Contract, a Public Liability Policy.

The policy shall:

be in the joint names of the parties;

cover the:

respective rights and interests; and

liabilities to third parties,

of the parties, the Superintendent, Consultants and Subcontractors from time to time, whenever engaged in WUC, and:

cover the parties’ respective liability to each other for loss or damage to property (other than property required to be insured by clause 16A) and the death of or injury to any person (other than liability which the law requires to be covered under a workers compensation insurance policy);

be endorsed to cover the use of any Construction Plant not covered under a comprehensive or third party motor vehicle insurance policy;

provide insurance cover for an amount in respect of any one occurrence of not less than the sum in Item 25(b); and

be with an insurer and otherwise in terms both approved in writing by the Principal (which approvals shall not be unreasonably withheld).

Insurance of employees

Before commencing WUC, the Contractor shall insure against statutory and common law liability for death of or injury to persons employed by the Contractor. The insurance cover shall be maintained until completion of all WUC.

Where permitted by law, the insurance policy or policies shall be extended to provide indemnity for the Principal’s statutory liability to the Contractor’s employees.

The Contractor shall ensure that all Consultants and Subcontractors have similarly insured their employees.

Inspection and provisions of insurance policies

Proof of insurance

Before the Contractor commences WUC and whenever requested in writing by the Principal, the Contractor shall provide satisfactory evidence of such insurance effected and maintained.

Insurance shall not limit liabilities or obligations under other provisions of the Contract.

Failure to produce proof of insurance

If after being so requested, the Contractor fails promptly to provide evidence of satisfactory compliance, then without prejudice to other rights or remedies, the Principal may insure and the cost thereof shall be certified by the Superintendent as moneys due and payable from the Contractor to the Principal. The Principal may refuse payment until such evidence is produced by the Contractor.

Notices from or to insurer

The Contractor shall ensure that each insurance policy contains provisions acceptable to the Principal which:

requires the insurer to inform the Principal, whenever the insurer gives a party or a Consultant or a Subcontractor a notice in connection with the policy;

provides that a notice of Claim given to the insurer by either party, the Superintendent, a Consultant or a Subcontractor shall be accepted by the insurer as a notice of Claim given by both parties, the Superintendent, the Consultant and the Subcontractor; and

requires the insurer, whenever the party fails to maintain the policy, promptly to give written notice thereof to both parties and prior to cancellation of the policy.

Notices of potential Claims

A party shall, as soon as practicable, inform the other party in writing of any occurrence that may give rise to a Claim under an insurance policy required by clause 16A or 17 and shall keep the other party informed of subsequent developments concerning the Claim. The Contractor shall ensure that Consultants and Subcontractors in respect of their operations similarly inform the parties.

Settlement of Claims

Upon settlement of a Claim under the insurance required by clause 16A:

to the extent that reinstatement has been the subject of a payment or allowance by the Principal to the Contractor, if the Contractor has not completed such reinstatement, insurance moneys received shall, if requested by either party, be paid into an agreed bank account in the joint names of the parties. As the Contractor reinstates the loss or damage, the Superintendent shall certify against the joint account for the cost of reinstatement; and

to the extent that reinstatement has not been the subject of a payment or allowance by the Principal to the Contractor, the Contractor shall be entitled immediately to receive from insurance moneys received, the amount of such moneys so paid in relation to any loss suffered by the Contractor.

Cross liability

Any insurance required to be effected in joint names in accordance with the Contract shall include a cross liability clause in which the insurer agrees to waive all rights of subrogation or action against any of the persons constituting the insured and for the purpose of which the insurer accepts the term ‘insured’ as applying to each of the persons constituting the insured as if a separate policy of insurance had been issued to each of them (subject always to the overall sum insured not being increased thereby).

Superintendent

The Principal shall ensure that at all times there is a Superintendent, and that the Superintendent fulfils all aspects of the role and functions in accordance with the relevant requirements of the Contract.

The following clauses are certifying functions of the Superintendent under the contract: subclause 34.5 (Extension of time), subclause 34.9 (Delay damages), subclause 36.4 (Pricing), subclause 37.2 (Certificates), subclause 34.6 (Practical completion) and subclause 37.4 (Final Payment Claim and Certificate). In carrying out all other non-certifying functions under the Contract, the Contractor acknowledges and agrees that the Superintendent is acting as agent for and on behalf of the Principal.

Except where the Contract otherwise provides, the Superintendent may give a Direction orally but shall as soon as practicable confirm it in writing. If the Contractor in writing requests the Superintendent to confirm an oral Direction, the Contractor shall not be bound to comply with the Direction until the Superintendent does so.

The Superintendent shall have:

access to the Site and the Work under the Contract; and

after reasonable notice to the Contractor, access to any place other than the Site where work under the Contract is being carried out or materials are being prepared or stored,

for the purposes of discharging the functions of the Superintendent under the Contract.

Superintendent’s Representative

The Superintendent may from time to time appoint individuals to exercise delegated Superintendent's functions, provided that:

no aspect of any function shall at any one time be the subject of delegation to more than one Superintendent’s Representative;

delegation shall not prevent the Superintendent exercising any function;

the Superintendent forthwith gives the Contractor written notice of respectively:

the appointment, including the Superintendent’s Representative’s name and delegated functions; and

the termination of each appointment; and

if the Contractor makes a reasonable objection to the appointment of a Superintendent’s Representative, the Superintendent shall terminate the appointment.

Contractor’s representative

The Contractor shall superintend WUC personally or by a competent representative. Matters within a Contractor’s representative’s knowledge (including Directions received) shall be deemed to be within the Contractor’s knowledge.

The Contractor shall forthwith give the Superintendent written notice of the representative’s name and any subsequent changes.

If the Superintendent makes a reasonable objection to the appointment of a representative, the Contractor shall terminate the appointment and appoint another representative.

Contractor’s employees and subcontractors

The Superintendent may direct the Contractor to have removed, within a stated time, from the Site or from any activity of WUC, any person employed on WUC who, in the Superintendent's opinion, is incompetent, negligent or guilty of misconduct.

Site

Access

Provided the Contractor has complied with subclauses 5.1 and 19.1 and any directions issued pursuant to clauses 12, 29.1, 30.1 and 32, the Principal shall by the time after Delivery Phase Approval for each Stage detailed in Item 26(a), give the Contractor sufficient access to each Site for commencement of WUC on Site. If the Principal has not given has not given the Contractor access to the whole of the relevant Site, the Principal shall give the Contractor access to such portions of the relevant Site as may, from time to time, be necessary for carrying out WUC. Subject to the next paragraph and subclause 39.7, delay by the Principal in giving access shall not be a breach of the Contract.

At any time up to the day 28 days before the date detailed in Item 26(a) the Principal may amend the date in Item 26(a). Any such amendment is not a breach of the Contract and the Contractor is not otherwise entitled to make any Claim arising out of or in connection with such amendment.

Access to each Site shall confirm on the Contractor a right to only such use and control as is necessary to enable the Contractor to carry out WUC and shall exclude camping, residential purposes and purposes not connected with WUC, unless approved by the Superintendent.

Access for Principal and others

The Principal and the Principal’s employees, consultants and agents may at any time after reasonable written notice to the Contractor, have access to any part of the Site for any purpose. The Contractor shall permit persons engaged by the Principal to carry out Work on the Site other than WUC and shall cooperate with them. The Principal shall give to the Contractor the names and roles of the persons so engaged.

The Contractor shall at all reasonable times give the Superintendent access to WUC.

The Principal shall ensure that none of the persons referred to in this subclause impedes the Contractor.

Minerals, fossils and relics

Valuable minerals, fossils, articles or objects of antiquity or of anthropological or archaeological interest, treasure trove, coins and articles of value found on the Site shall as between the parties be and remain the property of the Principal. Immediately upon the discovery of these things the Contractor shall:

take precautions to prevent their loss, removal or damage; and

give the Superintendent written notice of the discovery.

All costs so incurred by the Contractor shall be assessed by the Superintendent and added to the Contract Sum.

Latent conditions

Scope

Any latent structural defect in the existing buildings at each Site which:

differs materially from that which should have been anticipated at the Date of Delivery Phase Approval by a prudent, competent and experienced contractor if it had:

undertaken those site investigations and inspections which the Contractor had a reasonable opportunity to undertake including as part of the Due Diligence (regardless of whether they were actually undertaken); and

examined all documents and other information reasonably available to the Contractor including by the making of reasonable enquiries; and

requires repair or replacement work, not otherwise within the scope of the Works (whether expressly or by reasonable inference), but without which the Works as constructed will not be fit for their intended purpose.

Notification

The Contractor, upon becoming aware of a Latent Condition while carrying out WUC, shall promptly, and where possible before the Latent Condition is disturbed, give the Superintendent written notice of the general nature thereof.

If required by the Superintendent promptly after receiving that notice, the Contractor shall, as soon as practicable, give the Superintendent a written statement of:

the Latent Condition encountered and the respects in which it differs materially from the physical conditions which should reasonably have been anticipated by an experienced and competent contractor as required by subclause 25.1;

the additional Work, resources, time and cost which the Contractor estimates to be necessary to deal with the Latent Condition; and

other details reasonably required by the Superintendent.

Deemed variation

Subject to the Contractor complying with subclause 25.2, if in the Superintendent’s opinion, the Latent Condition causes the Contractor to:

carry out more work; or

incur more cost,

than the Contractor could reasonably have anticipated at the relevant Date of Delivery Phase Agreement, a valuation for all reasonable costs directly and necessarily incurred by reason of the Latent Condition after the date of the notice under subclause 25.2 (but otherwise with no entitlement to make a Claim) shall be valued under subclause 36.4.

Not Used

Cleaning up

The Contractor shall keep the Site and WUC clean and tidy and regularly remove rubbish and surplus material.

Within 14 days after the Date of Practical Completion of a Stage, the Contractor shall remove the relevant Temporary Works and Construction Plant. The Superintendent may extend the time to enable the Contractor to perform remaining obligations.

If the Contractor fails to comply with the preceding obligations in this clause, the Superintendent may direct the Contractor to rectify the non-compliance and the time for rectification.

If:

the Contractor fails to comply with such a Directions; and

that failure has not been made good within 5 days after the Contractor receives written notice from the Superintendent that the Principal intends to have the subject Work carried out by others,

the Principal may have that Work so carried out and the Superintendent shall certify the cost incurred as moneys due from the Contractor to the Principal. The rights given by this paragraph are additional to any other rights and remedies.

Materials, labour and Construction Plant

Except where the Contract otherwise provides, the Contractor shall supply everything necessary for the proper performance of the Contractor’s obligations and discharge of the Contractor’s liabilities.

In respect of any materials, machinery or equipment to be supplied by the Contractor in connection with the Contract, the Superintendent may direct the Contractor to:

supply particulars of the mode and place of manufacture, the source of supply, the performance capacities and other related information; and

arrange reasonable inspection at such place or sources by the Superintendent, the Principal and persons authorised by the Principal.

The Superintendent may give the Contractor a written Direction not to remove materials or Construction Plant from the Site. Thereafter the Contractor shall not remove them without the Superintendent's prior written approval (which shall not be unreasonably withheld).

Quality

Quality of material and work

Unless otherwise provided, the Contractor shall use suitable new materials and proper and tradesmanlike workmanship.

*

Quality assurance

If the Contract elsewhere requires further quality assurance, the Contractor shall:

plan, establish and maintain a conforming quality system; and

ensure that the Superintendent has access to the quality system of the Contractor, Consultants and Subcontractors so as to enable monitoring and quality auditing.

Any such quality system shall be used only as an aid to achieving compliance with the Contract and to document such compliance. Such system shall not discharge the Contractor’s other obligations under the Contract.

Defective work

If the Superintendent becomes aware of Work done (including material provided) by the Contractor which does not comply with the Contract, the Superintendent shall as soon as practicable give the Contractor written details thereof. If the subject Work has not been rectified, the Superintendent may direct the Contractor to do any one or more of the following (including times for commencement and completion):

remove the material from the Site;

demolish the Work;

redesign, reconstruct, replace or correct the Work; and

not deliver it to the Site.

If:

the Contractor fails to comply with such a Direction; and

that failure has not been made good within 8 days after the Contractor receives written notice from the Superintendent that the Principal intends to have the subject Work rectified by others,

the Principal may have that Work so rectified and the Superintendent shall certify the cost incurred as moneys due from the Contractor to the Principal.

Acceptance of defective work

Instead of a Direction pursuant to subclause 29.3, the Superintendent may direct the Contractor that the Principal elects to accept the subject Work, whereupon there shall be a deemed Variation.

If the Superintendent's determines that the subject work is worth less or has cost less for the Contractor to carry out than the work which is in accordance with the Contract, then the Variation shall be valued in accordance with subclause 36.4 and the relevant Contract Sum (Stage) adjusted accordingly.

Timing

The Superintendent may give a Direction pursuant to this clause at any time before the expiry of the last Defects Liability Period.

Examination and testing

Tests

At any time before the expiry of the [last Defects Liability Period], the Superintendent may direct that any WUC be tested. The Contractor shall give such assistance and samples and make accessible such parts of WUC as may be directed by the Superintendent.

Covering up

The Superintendent may direct that any part of WUC shall not be covered up or made inaccessible without the Superintendent's prior written Direction.

Who conducts

Tests shall be conducted as provided elsewhere in the Contract or by the Superintendent or a person (which may include the Contractor) nominated by the Superintendent.

Notice

The Superintendent or the Contractor (whichever is to conduct the Test) shall give reasonable written notice to the other of the date, time and place of the Test. If the other does not attend, the Test may nevertheless proceed.

Delay

Without prejudice to any other right, if the Contractor or the Superintendent delays in conducting a Test, the other, after giving reasonable written notice of intention to do so, may conduct the Test.

Completion and results

On completion of the Tests, the Contractor shall make good WUC so that it fully complies with the Contract.

Results of Tests shall be promptly made available by each party to the other and to the Superintendent.

Costs

Costs in connection with testing pursuant to this clause shall be borne by the Principal except where the Contract otherwise provides or the Test is consequent upon, or reveals a failure of the Contractor to comply with the Contract (including this clause).

Working hours

If the working hours and working days on the Site are as stated in the Principal's Project Requirements. They shall not be varied without the Superintendent's prior written approval, except when, in the interests of safety of persons or property, the Contractor finds it necessary to carry out WUC otherwise, whereupon the Contractor shall give the Superintendent written notice of those circumstances as early as possible.

Programming

The Superintendent shall give to the Contractor the information, materials, documents and instructions by the times or within the periods both stated in Item 27.

The Contractor shall give the Superintendent reasonable advance notice of when the Contractor needs other information, materials, documents or instructions from the Superintendent or the Principal.

The Principal and the Superintendent shall not be obliged to give any information, materials, documents or instructions earlier than the Principal or the Superintendent, as the case may be, should reasonably have anticipated at the Date of the Contract.

The Superintendent may direct in what order and at what time the various stages or portions of WUC shall be carried out. If the Contractor can reasonably comply with the Direction, the Contractor shall do so. If the Contractor cannot reasonably comply, the Contractor shall give the Superintendent written notice of the reasons.

The Contractor must:

update the Program from time to time (and at least monthly) to take account of delays or changes to the Program;

give the Superintendent copies of all Programs; and

provide all Programs in a format compatible with the software directed by the Superintendent

The Contractor shall not, without reasonable cause and reasonable prior notice to the Superintendent setting out the cause and seeking its prior approval to the departure, depart from a Program.

The Contractor shall update the Program from time to time when requested by the Superintendent to reflect only approved extensions of time, approved variations and any departure from the Contractor's Program approved by the Superintendent. The Contractor shall immediately provide a copy of any updated Program to the Superintendent.

If the Contractor fails to furnish a Program or updated Program following a request by the Superintendent, the Principal may withhold payment of any amounts otherwise due to the Contractor until the Contractor remedies such failure. The rights given in this clause 32 are in addition to any other rights of the Principal

Suspension

Superintendent’s suspension

The Superintendent may direct the Contractor to suspend the carrying out of the whole or part of WUC for such time as the Superintendent thinks fit, if the Superintendent is of the opinion that it is necessary:

because of an act, default or omission of:

the Superintendent, the Principal or its employees, consultants, agents or other contractors (not being employed by the Contractor); or

the Contractor, a Consultant, a Subcontractor or the employees or agents of any of them;

for the protection or safety of any person or property; or

to comply with a court order.

Contractor’s suspension

If the Contractor wishes to suspend the carrying out of the whole or part of WUC, otherwise than pursuant to subclause 39.9, the Contractor shall obtain the Superintendent's prior written approval. The Superintendent may approve the suspension and may impose conditions of approval.

Recommencement

As soon as the Superintendent becomes aware that the reason for any suspension no longer exists, the Superintendent shall direct the Contractor to recommence suspended WUC as soon as reasonably practicable.

The Contractor may recommence WUC suspended pursuant to subclause 33.2 or 39.9 at any time after reasonable notice to the Superintendent.

Cost

The Contractor shall bear the cost of suspension pursuant to paragraph (a)(ii) of subclause 33.1 and subclause 33.2. If the Contractor made the protection, safety, court order or suspension of work necessary, the Contractor shall bear the cost of suspension pursuant to paragraph (b) or (c) of subclause 33.1. If the Contractor otherwise incurs more or less cost than otherwise would have been incurred, the difference shall be assessed by the Superintendent and added to or deducted from the relevant Contract Sum (Stage).

Time and progress

Progress

The Contractor shall ensure that the WUC for each Stage reaches Practical Completion by the relevant Date for Practical Completion.

Notice of delay

A party becoming aware of anything which will probably cause delay to WUC shall promptly give the Superintendent and the other party written notice of that cause and the estimated delay.

Claim

Subject to it complying with the relevant requirements of subclause 34.2, the Contractor shall be entitled to such EOT to the relevant Date for Practical Completion as the Superintendent assesses ('EOT’), if the Contractor is, or is likely to be delayed.

The Contractor shall be entitled to such EOT for carrying out WUC (including reaching Practical Completion) as the Superintendent assesses, if:

the Contractor is or will be delayed in reaching Practical Completion of a Stage by delays affecting critical path activities caused by a Qualifying Cause of Delay; and

the Contractor gives the Superintendent, within 14 days of when the Contractor should reasonably have become aware of that causation occurring, a written Claim for an EOT evidencing the facts of causation and of the delay to WUC (including extent).

If further delay results from a Qualifying Cause of Delay evidenced in a Claim under paragraph (b) of this subclause, the Contractor shall claim an EOT for such delay by promptly giving the Superintendent a written Claim evidencing the facts of that delay.

The Contractor acknowledges and agrees that it is not entitled to claim any additional cost or expense, any adjustment to the Contract Sum, or to Claim an EOT or any Claim otherwise at law, if it has failed to comply with subclauses 34.2 and 34.3.

Assessment

When both non-qualifying and Qualifying Causes of Delay overlap, the Superintendent shall apportion the resulting delay to WUC according to the respective causes’ contribution.

In assessing each EOT the Superintendent shall disregard questions of whether:

the WUC for the relevant Stage can nevertheless reach Practical Completion without an EOT; or

the Contractor can accelerate,

but shall have regard to what prevention and mitigation of the delay has not been effected by the Contractor.

Extension of time

Within 14 days after receiving the Contractor’s Claim for an EOT, the Superintendent may request further information from the Contractor in respect of any Claim for an EOT. The Contractor must provide the information requested to the Superintendent within the time and in the form requested by the Superintendent before the Superintendent is required to assess the Contractor’s Claim for an EOT.

Within 28 days after receiving the Contractor’s Claim or any further information requested by the Superintendent for an EOT, the Superintendent shall give to the Contractor and the Principal a written Direction evidencing the EOT so assessed.

Notwithstanding that the Contractor is not entitled to or has not claimed an EOT, the Superintendent may at any time and from time to time before issuing the Final Certificate for a Stage direct an EOT.

For the avoidance of doubt, the exercise of the power in the previous paragraph of this clause shall be at the absolute discretion of the Superintendent and nothing in this clause shall entitle the Contractor to an EOT where that entitlement has been released in accordance with subclause 34.3.

Any failure by the Superintendent to grant a reasonable EOT or to comply with any of the requirements of this clause shall not cause the relevant Date for Practical Completion to be set at large. The Contractor may refer any decision of the Superintendent for dispute resolution under clause 43 and, subject to the Contract, the decision shall be reviewable. Under no circumstances will a failure to grant a reasonable EOT or a delay in granting an EOT entitle the Contractor to damages or compensation, whether under the Contract, in tort, in equity, under statute or otherwise.

Practical completion

The Contractor shall give the Superintendent at least 14 days written notice of the date upon which the Contractor anticipates that Practical Completion of a Stage will be reached.

When the Contractor is of the opinion that Practical Completion has been reached, the Contractor shall in writing request the Superintendent to issue a certificate of Practical Completion. Within 14 days after receiving the request, the Superintendent shall give the Contractor and the Principal either a Certificate of Practical Completion evidencing the Date of Practical Completion or written reasons for not doing so.

If the Superintendent is of the opinion that Practical Completion has been reached, the Superintendent may issue a Certificate of Practical Completion even though no request has been made.

Liquidated damages

If WUC does not reach Practical Completion of a Stage by the relevant Date for Practical Completion, the Superintendent shall certify, as due and payable to the Principal, the relevant liquidated damages in Item 29 for every day after the Date for Practical Completion to and including the earliest of the Date of Practical Completion or termination of the Contract or the Principal taking WUC out of the hands of the Contractor.

If an EOT is directed after the Contractor has paid or the Principal has set off liquidated damages, the Principal shall forthwith repay to the Contractor such of those liquidated damages as represent the days the subject of the EOT.

Not used

Delay damages

For every day the subject of an EOT in respect of a Stage for a Compensable Cause and for which the Contractor gives the Superintendent a Claim pursuant to subclause 42.1 for extra costs reasonably incurred by the Contractor ('Delay Costs'), Delay Costs certified by the Superintendent under subclause 42.3 shall be due and payable to the Contractor, up the daily limit specified in Item 30.

Defects liability

The Defects Liability Period in respect of a Stage shall commence at 4:00 pm on the Date of Practical Completion of that Stage.

The Contractor shall carry out rectification at times and in a manner causing as little inconvenience to the occupants or users of the Stage is reasonably possible.

As soon as possible after the Date of Practical Completion, the Contractor shall rectify all Defects existing at the Date of Practical Completion.

During the Defects Liability Period, the Superintendent may give the Contractor a Direction to rectify a Defect which:

shall identify the Defect and the date for completion of its rectification; and

may state a date for commencement of the rectification and whether there shall be a separate Defects Liability Period therefor commencing at 4:00 pm on the date the rectification is completed and governed by this clause).

If the rectification is not commenced or completed by the stated dates, the Principal may have the rectification carried out by others but without prejudice to any other rights and remedies the Principal may have. The cost thereby incurred shall be certified by the Superintendent as moneys due and payable to the Principal.

Variations

Directing variations

The Contractor shall not vary WUC except as directed in writing.

The Superintendent, before the Date of Practical Completion of a Stage, may direct the Contractor to vary the WUC for the relevant Stage by any one or more of the following which is nevertheless of a character and extent contemplated by, and capable of being carried out under, the provisions of the Contract (including being within the warranties in subclause 2.2):

increase, decrease or omit any part;

change the character or quality;

change the levels, lines, positions or dimensions;

carry out additional Work;

demolish or remove material or Work no longer required by the Principal.

Notwithstanding any other provision of the Contract, the approval of the Principal or the Superintendent to anything or the failure to disapprove of anything, shall not be taken to be a Variation. A Variation shall only occur if the Superintendent has directed in writing the Contractor to do one or more of the things listed in this clause 36.1 and either:

          - the Direction is stated to be a variation instruction; or

prior to the Contractor commencing to comply with the Direction, the Superintendent has confirmed in writing to the Contractor that the Direction will be regarded as a Variation; or

the Superintendent has determined under paragraph (b) that the Direction is not to be regarded as a variation, but the Contractor, prior to commencing to comply with the Direction, has given a notice of Dispute under subclause 43.1 in relation to that determination and such Dispute is resolved or determined in favour of the Contractor.

Otherwise, any work carried out by the Contractor shall be deemed not to be a Variation and the Contractor will have no Claim against the Principal (or the Superintendent).

Proposed variations

The Superintendent may give the Contractor written notice of a proposed variation.

The Contractor shall as soon as practicable after receiving such notice, notify the Superintendent whether the proposed variation can be effected, together with, if it can be effected, the Contractor’s estimate of the:

effect on the relevant Program (including the relevant Date for Practical Completion); and

cost (including all warranties and time-related costs, if any) of the proposed variation.

The Superintendent may direct the Contractor to give a detailed quotation for the proposed variation supported by measurements or other evidence of cost.

Variations for convenience of Contractor

If the Contractor requests the Superintendent to direct a Variation for the convenience of the Contractor, the Superintendent may do so. The Direction shall be written and may be conditional. Unless the Direction provides otherwise, the Contractor shall be entitled to neither extra time nor extra money.

Pricing

The Superintendent shall, as soon as possible, price each Variation using the following order of precedence:

prior agreement;

applicable rates or prices in the Contract;

rates or prices in a Schedule of Rates or schedule of prices, even though not Contract documents, to the extent that it is reasonable to use them; and

reasonable rates or prices, which shall include a reasonable amount for profit and overheads,

and any deductions shall include a reasonable amount for profit but not overheads.

That price shall be added to or deducted from the relevant Contract Sum (Stage).

Payment

Progress claims

The Contractor shall claim payment progressively in accordance with Item 33.

An early progress claim shall be deemed to have been made on the date for making that claim.

Each progress claim shall be given in writing to the Superintendent and shall include details of the value of WUC done and may include details of other moneys then due to the Contractor pursuant to provisions of the Contract.

Full supporting documentation to the reasonable satisfaction of the Superintendent must be provided to the Superintendent with each progress claim.

Certificates

The Superintendent shall, within 14 days after receiving such a progress claim, issue to the Principal and the Contractor:

a Progress Certificate evidencing the Superintendent's opinion of the moneys due from the Principal to the Contractor pursuant to the progress claim and reasons for any difference (‘Progress Certificate'); and

a certificate evidencing the Superintendent's assessment of moneys due from the Contractor to the Principal pursuant to the Contract.

If the Contractor does not make a progress claim in accordance with Item 33, the Superintendent may issue the Progress Certificate with details of the calculations and shall issue the certificate in paragraph (b).

If the Superintendent does not issue the Progress Certificate within 14 days of receiving a progress claim in accordance with subclause 37.1, that progress claim shall be deemed to be the relevant Progress Certificate.

The Principal shall within 7 days after receiving both such certificates, or within 21 days after the Superintendent receives the progress claim, pay to the Contractor the balance of the Progress Certificate after setting off such of the certificate in paragraph (b) as the Principal elects to set off. If that setting off produces a negative balance, the Contractor shall pay that balance to the Principal within 7 days of receiving written notice thereof.

Neither a Progress Certificate nor a payment of moneys shall be evidence that the subject WUC has been carried out satisfactorily. Payment other than Final Payment shall be payment on account only.

Unfixed plant and materials

The Principal shall not be liable to pay for unfixed plant and materials unless they are listed in Item 34 and the Contractor:

provides the additional Security in Item 14(e); and

satisfies the Superintendent that the subject plant and materials have been paid for, properly stored and protected, and labelled the property of the Principal.

Upon payment to the Contractor and the release of any additional Security in paragraph (a), the subject plant and materials shall be the unencumbered property of the Principal.

Final payment claim and certificate

Within 28 days after the expiry of the Defects Liability Period in respect of a Stage, the Contractor shall give the Superintendent a written Final Payment Claim endorsed ‘Final Payment Claim’ being a progress claim together with all other Claims whatsoever in connection with the relevant Stage.

Within 42 days after the expiry of that last Defects Liability Period, the Superintendent shall issue to both the Contractor and the Principal a Final Certificate evidencing the moneys finally due and payable between the Contractor and the Principal on any account whatsoever in connection with the relevant Stage ('Final Payment').

Those moneys certified as due and payable shall be paid by the Principal or the Contractor, as the case may be within 7 days after the debtor receives the Final Certificate.

Interest

Interest in Item 35 shall be due and payable after the date of default in payment.

Other moneys due

The Principal may deduct from moneys otherwise due to the Contractor:

any debt or other moneys due from the Contractor to the Principal; and

any Claim to money which the Principal may have against the Contractor whether for damages (including liquidated damages) or otherwise,

- whether under the Contract or otherwise at law relating to the Works.

- The Principal may also elect that moneys due and owing to the Contractor otherwise than in connection with the subject matter of the Contract also be due to the Principal pursuant to the Contract.

Payment of workers, consultants and subcontractors

Workers, consultants and subcontractors

The Contractor shall give in respect of a progress claim, documentary evidence of the payment of moneys due and payable to:

workers of the Contractor and of the Subcontractors;

Consultants; and

Subcontractors,

in respect of WUC the subject of that Claim.

If the Contractor is unable to give such documentary evidence, the Contractor shall give other documentary evidence of the moneys so due and payable to workers, Consultants and Subcontractors.

Documentary evidence, except where the Contract otherwise provides, shall be to the Superintendent's satisfaction.

Withholding payment

Subject to the next paragraph, the Principal may withhold moneys certified due and payable in respect of the progress claim until the Contractor complies with subclause 38.1.

The Principal shall not withhold payment of such moneys in excess of the moneys evidenced pursuant to subclause 38.1 as due and payable to workers, Consultants and Subcontractors.

Direct payment

Before Final Payment, the Principal, if not aware of a relevant relation-back day (as defined in the Corporations Law) may pay unpaid moneys the subject of subclause 38.1 directly to a worker, Consultant or Subcontractor where:

permitted by law;

given a court order in favour of the worker, Consultant or Subcontractor; or

requested in writing by the Contractor.

Such payment and a payment made to a worker, Consultant or Subcontractor in compliance with a Legislative Requirement shall be deemed to be part-satisfaction of the Principal’s  obligation to pay pursuant to subclause 37.2 or 37.4, as the case may be.

Default or insolvency

Preservation of other rights

If a party breaches (including repudiates) the Contract, nothing in this clause shall prejudice the right of the other party to recover damages or exercise any other right or remedy.

Contractor’s default

If the Contractor commits a substantial breach of the Contract, the Principal may, by hand or by registered post, give the Contractor a written notice to rectify the breach.

Substantial breaches include, but are not limited to:

failing to:

perform properly the Contractor’s Design Obligations;

provide Security;

provide evidence of insurance;

comply with a Direction of the Superintendent pursuant to subclause 29.3; or

use the materials or standards of Work required by the Contract;

wrongful suspension of Work;

substantial departure from a Program without reasonable cause or the Superintendent's approval;

failing to proceed with due expedition and without delay; and

in respect of clause 38, knowingly providing documentary evidence containing an untrue statement.

Principal’s notice to rectify

A notice under subclause 39.2 shall state:

that it is a notice under clause 39 of these General Conditions;

the alleged substantial breach; and

the date and time by which the Contractor must rectify the breach (which shall not be less than 7 clear days after the notice is received by the Contractor).

Principal’s rights

If the Contractor fails to rectify the breach by the stated date and time, the Principal may by written notice to the Contractor:

take out of the Contractor’s hands the whole or part of the Work remaining to be completed and suspend payment until it becomes due and payable pursuant to subclause 39.6; or

terminate the Contract.

Take out

The Principal shall complete Work taken out of the Contractor’s hands and may:

use materials, equipment and other things intended for WUC; and

without payment of compensation to the Contractor:

take possession of, and use, such of the Construction Plant and other things on or in the vicinity of the Site as were used by the Contractor;

contract with such of the Consultants and Subcontractors; and

take possession of, and use, such of the Design Documents,

as are reasonably required by the Principal to facilitate completion of WUC taken out.

If the Principal takes possession of Construction Plant, Design Documents or other things, the Principal shall maintain them and, subject to subclause 39.6, on completion of the Work taken out, shall return such of them as are surplus.

The Superintendent shall keep records of the cost of completing the Work taken out.

Adjustment on completion of work taken out

When Work taken out of the Contractor’s hands has been completed, the Superintendent shall assess the cost thereby incurred and shall certify as moneys due and payable accordingly the difference between that cost (showing the calculations therefor) and the amount which would otherwise have been paid to the Contractor if the Work had been completed by the Contractor.

If the Contractor is indebted to the Principal, the Principal may retain Construction Plant or other things taken under subclause 39.5 until the debt is satisfied. If after reasonable notice, the Contractor fails to pay the debt, the Principal may sell the Construction Plant or other things and apply the proceeds to the satisfaction of the debt and the costs of sale. Any excess shall be paid to the Contractor.

Principal’s default

If the Principal commits a substantial breach of the Contract, the Contractor may, by hand or by registered post, give the Principal a written notice to rectify the breach.

Substantial breaches include, but are not limited to:

failing to:

rectify inadequate Contractor’s access to the Site if that failure continues for longer than the time stated in Item 36(a); or

make a payment due and payable pursuant to the Contract; and

the Superintendent not giving a Certificate of Practical Completion or reasons as referred to in subclause 34.6.

Contractor’s notice to rectify

A notice given under subclause 39.7 shall state:

that it is a notice under clause 39 of these General Conditions;

the alleged substantial breach; and

the date and time by which the Principal must rectify the breach (which shall not be less than 7 clear days after the notice is received by the Principal).

Contractor’s rights

If the Principal fails to rectify the breach by the stated date and time, the Contractor may, by written notice to the Principal, suspend the whole or any part of WUC.

The Contractor shall remove the suspension if the Principal remedies the breach.

The Contractor may, by written notice to the Principal, terminate the Contract, if within 28 days of the date of suspension under this subclause the Principal fails:

to remedy the breach; or

if the breach is not capable of remedy, to make other arrangements to the reasonable satisfaction of the Contractor.

Damages suffered by the Contractor by reason of the suspension shall be assessed by the Superintendent, who shall certify them as moneys due and payable to the Contractor.

Termination

If the Contract is terminated pursuant to subclause 39.4(b) or 39.9, the parties’ remedies, rights and liabilities shall be the same as they would have been under the law governing the Contract had the defaulting party repudiated the Contract and the other party elected to treat the Contract as at an end and recover damages.

If the Contract is wrongfully terminated by a party, the other party, having elected to accept repudiation of the Contract, shall then only be entitled to recover damages in respect of the wrongful termination of the Contract and shall not be entitled to claim on a quantum meruit basis.

The Principal may, without payment of compensation, take possession of the Design Documents.

Insolvency

If:

a party informs the other in writing, or creditors generally, that the party is insolvent or is financially unable to proceed with the Contract;

execution is levied against a party by a creditor;

a party is an individual person or a partnership including an individual person, and if that person:

commits an act of bankruptcy;

has a bankruptcy petition presented against him or her or presents his or her own petition;

is made bankrupt;

makes a proposal for a scheme of arrangement or a composition; or

has a deed of assignment or deed of arrangement made, accepts a composition, is required to present a debtor’s petition, or has a sequestration order made, under Part X of the Bankruptcy Act 1966 (Cwlth) or like provision under the law governing the Contract;

in relation to a party being a corporation:

notice is given of a meeting of creditors with a view to the corporation entering a deed of company arrangement;

it enters a deed of company arrangement with creditors;

a controller or administrator is appointed;

an application is made to a court for its winding up and not stayed within 14 days;

a winding up order is made in respect of it;

it resolves by special resolution that it be wound up voluntarily (other than for a member’s voluntary winding up); or

a mortgagee of any of its property takes possession of that property,

then, where the other party is:

the Principal, the Principal may, without giving a notice to rectify the breach exercise the right under subclause 39.4(a); or

the Contractor, the Contractor may, without giving a notice to rectify the breach, exercise the right under subclause 39.9; or

a party is unable to pay its debts as and when they fall due.

The rights and remedies given by this subclause are additional to any other rights and remedies. They may be exercised notwithstanding that there has been no breach of contract.

Termination for Convenience

In addition to any other right under the Contract the parties acknowledge and agree that:

the Contract may be terminated at any time by the Principal giving reasonable prior written notice to the Contractor.

If the Contract is terminated pursuant to this clause, the Principal shall pay the Contractor:

for Work carried out prior to the date of termination, the amount which would have been payable if the Contract had not been terminated and the Contractor submitted a progress claim for Work carried out to the date of termination for the Works carried out up to and including the date of termination; and

the cost of goods or materials reasonably ordered by the Contractor for the Works for which the Contractor is legally bound to pay provided that:

the value of the goods or materials is not included in the amount payable under subclause 40(b)(i); and

title in the goods and materials will vest in the Principal upon payment

upon termination any payment of the amount due to the Contractor under this clause, the Contractor shall deliver to the Principal the contract material which has been prepared up to the date of termination regardless of the stage of completion of the Works but without any liability in respect of the contract material which is incomplete by reason only of such termination.

Not Used

Notification of Claims

Communication of Claims

Except for claims for:

an EOT under subclause 34.5;

payment under subclauses 37.2 and 37.4 of the original Contract Sum or any part thereof; or

a Variation directed by the Principal in writing under subclause 36.1,

the Contractor must give the Superintendent the notices required by subclause 42.2 if it wishes to make a Claim against the Principal in respect of any direction by the Principal or the Superintendent or any other fact, matter or thing (including a breach of the Contract by the Principal) under, arising out of, or in any way in connection with, WUC or the Contract.

Prescribed notices

The notices referred to in subclause 42.1 are:

a written notice within 7 days of the first occurrence of the Direction or other fact, matter or thing upon which the Claim is based, expressly specifying:

that the Contractor proposes to make a Claim; and

the Direction or other fact, matter or thing upon which the Claim will be based; and

a written Claim within 7 days of giving the written notice under subclause 42.2(a), which must include:

detailed particulars concerning the direction or other fact, matter or thing upon which the Claim is based;

the legal basis for the Claim, whether based on a term of the Contract or otherwise, and if based on a term of the Contract, clearly identifying the specific term;

the facts relied upon in support of the Claim in sufficient detail to permit verification; and

details of the amount claimed and how it has been calculated,

Superintendent’s decision

If within 14 days of giving the notice under subclause 42.2(a) the party giving it does not notify the other party and the Superintendent of particulars of the Claim in accordance with subclause 42.2(b), the notice under subclause 42.2(a) shall be deemed to be the Claim.

Within 28 days of receipt of the Prescribed Notice the Superintendent shall assess the Claim and notify the parties in writing of the decision.

Time bar

If the Contractor fails to comply with subclauses 34.5, 42.1 or 42.2:

the Principal will not be liable upon any Claim by the Contractor; and

the Contractor will be absolutely barred from making any Claim against the Principal,

- arising out of, or in any way in connection with, the relevant direction or fact, matter or thing (as applicable) to which subclauses 34.5, 42.1 or 42.2 applies.

Dispute resolution

Notice of dispute

If a difference or dispute (together called a ‘Dispute') between the parties arises in connection with the subject matter of the Contract, including a Dispute concerning:

a Superintendent’s Direction; or

a Claim,

then either party shall, by hand or by registered post, give the other and the Superintendent a written notice of Dispute adequately identifying and providing details of the Dispute.

Notwithstanding the existence of a Dispute, the parties shall, subject to clauses 39, 40(c) and subclause 43.4, continue to perform the Contract.

Conference

Within 14 days after receiving a notice of Dispute, the parties shall confer at least once to resolve the Dispute or to agree on methods of doing so. At every such conference each party shall be represented by a person having authority to agree to such resolution or methods. All aspects of every such conference except the fact of occurrence shall be privileged.

If the Dispute has not been resolved within 28 days of service of the notice of Dispute, that Dispute shall be and is hereby referred to litigation.

Not used

Summary relief

Nothing herein shall prejudice the right of a party to institute proceedings to enforce payment due under the Contract or to seek injunctive or urgent declaratory relief.

Waiver of conditions

Except as provided at law or in equity or elsewhere in the Contract, none of the terms of the Contract shall be varied, waived, discharged or released, except with the prior written consent of the parties.

Transparency and Accountability Requirements

The Principal is required to adhere to high standards of proprietary in the conduct of its activities. The Contractor will adhere to similar standards of proprietary in carrying out WUC.

The Principal is subject to certain transparency and accountability requirements of the laws and policies applying to the Commonwealth.

The Contractor acknowledges that these may include:

an obligation on the Principal to publish on the internet details of all contracts with a value of $10,000 or more, such details to include the name of the Contractor, the subject matter of the contract and whether the contract contains any provisions requiring the parties to maintain confidentiality and the reasons for those provisions;

a public right of access to official documents of the Principal under the Freedom of Information Act 1982 (Cth) subject to certain exemptions;

the protection of personal information under the Privacy Act 1988 (Cth);

obligations under the Workplace Gender Equality Act 2012 (Cth); and

providing information and evidence to Senate Committees, Ministers and other government officials.

The Contractor is deemed to have familiarised itself with these requirements and agrees:

to provide all information and assistance reasonably requested by the Principal to enable the Principal to comply with its transparency and accountability obligations;

not to do or omit to do anything which might place the Principal in breach of these obligations; and

not engage in conduct that is illegal, misleading and deceptive.

Industrial Relations

The Contractor shall be responsible for all employment and industrial disputes, issues and matters affecting the progress of WUC (whether caused or contributed to by the Contractor or its personnel or otherwise).

The Contractor must ensure that:

industrial relations at the Site are managed by an appropriately qualified person;

all relevant awards and workplace arrangements which have been certified, registered or otherwise approved are complied with;

it manages all industrial relations issues in such a way so as to ensure that a good industrial climate is maintained at the Site; and

all subcontractors engaged in WUC cooperate and assist in maintaining a good industrial climate at the Site.

Australian Government Building and Construction OHS Accreditation Scheme

The Contractor warrants that, as at the Date of the Contract, it is accredited under the Australian Government Building and Construction Industry OHS Accreditation Scheme ('Scheme') established by the Fair Work (Building Industry) Act 2012 (Cth).

The Contractor must:

          - comply with all conditions of Scheme accreditation;

          - maintain its accreditation under the Scheme until the expiry or earlier termination of this Contract, and

          - immediately notify the Principal if the Contractor's accreditation under the Scheme is, or is reasonably likely to be, revoked or suspended.

Without limiting any of the Principal's rights under the Contract, a failure by the Contractor to comply with its obligations under this clause 47 is a substantial breach of the Contract under subclause 39.2.

Taxes, Duties and Government Charges

Unless otherwise indicated, the Contract Sum is inclusive of all taxes, duties, charges and fees required to be paid in execution of the WUC.

- 48A    Papua New Guinea Duties

All scheduled goods imported by the Contractor into Papua New Guinea may be exempt from customs and other import duties, if the Principal’s prior written approval is obtained for import and the goods are imported in accordance with the protocols detailed in the Principal's Project Requirements.

Following agreement with the Superintendent on the dates for the submission of the relevant schedules and relevant Papua New Guinea authorities approving this approach, the Contractor is to provide two schedules detailing goods to be imported. The first schedule is to be a preliminary list of imported goods which will need to be imported during the early works and the second being the final list of imported goods that will be used in the execution of the Works.

The Principal shall endorse the necessary exemption documents prepared by the Contractor for presentation in order to clear the goods through Customs and shall also provide such other documentation reasonably required by the Superintendent.

If exemption is not then granted to the scheduled goods the customs duties payable and paid shall be reimbursed by the Principal.

All imported goods which are not incorporated in or expended in connection with the Works shall be re-exported upon the issue of the Final Certificate. If not exported the goods will be assessed for duties as applicable to the goods involved in accordance with the laws of Papua New Guinea.

However, exemption from duties may not be available for:

          - goods which are similar to those locally produced, unless they are not available in sufficient quantities or are of a different standard to that which is necessary for the Works, and

          - any element of duty or tax inherent in the price of goods or services procured in Papua New Guinea, which shall be deemed to be included in the Contract Sum (Aggregate).

Port dues, quay dues and (except as set out above) any element of tax or duty inherent in the price of goods or services shall be deemed to be included in the Contract Sum (Aggregate).

- 48B   Goods and Services Tax

The Contract Sum (Aggregate) and all other consideration for any supply made under this Contract are exclusive of any GST imposed on the supply.

If one party (the supplier) makes a taxable supply to the other party (the recipient) under this Contract, on receipt of a tax invoice from the supplier, the recipient will pay without set off an additional amount to the supplier equal to the GST imposed on the supply in question.

No party may claim or retain from the other party any amount in relation to a supply made under this Contract for which the first party can obtain an input tax credit or decreasing adjustment.

Work Health and Safety

Work Health and Safety obligations

The Contractor must comply and ensure compliance with:

          - all relevant Legislative Requirements, including codes of practice and national standards relating to work health and safety;

          - all policies relating to work health and safety which the Principal has directed are applicable to the carrying out of the Works', and

          - the WHS management plan, safe work method statement and any other WHS-related documentation submitted by the Contractors the Principal as part of the Contractor's tender for the Works (as well as the final version of those documents).

In the event of any inconsistency between the requirements of paragraphs a) and b), the Contractor will comply with that which imposes the higher level of work health and safety.

The Contractor agrees and acknowledges that for the purposes of the WHS Law, in

carrying out the WUC it:

          - is a person conducting a business or undertaking;

          - has been authorised by the Principal to have management and control of the site to the extent necessary to carry out the WUC; and

          - has been engaged by the Principal and has accepted appointment as the 'principal contractor' in relation to the work under the Contract.

The Contractor must comply with all the duties and obligations imposed on a 'principal contractor' under the WHS Law, including but not limited to:

          - complying with its health and safety duties in relation to all WUC;

          - complying with the consultation, representation and participation requirements, including any consultation required with designers and manufacturers;

          - preparing safe work method statements for high risk construction work and ensuring that the high risk construction work is carried out in accordance with the safe work method statements;

          - complying with all relevant codes of practice approved under the WHS Law;

          - immediately notifying the Principal of any 'notifiable incident' as defined in the WHS Law;

          - permitting work health and safety entry permit holders entry to the site; and

          - not permitting any act or omission that causes or may cause the Principal or the Contractor to not comply with the WHS Law.

Key Personnel

The Contractor shall ensure that the Key Personnel listed in Item 39 are dedicated to WUC and:

          - are available at all times to perform the Work for which they are nominated and at any other time requested by the Superintendent or the Principal;

          - are appropriately qualified, trained, instructed and skilled to carry out their respective roles and responsibilities;

          - attend all meetings requested by the Superintendent or the Principal; and

          - properly perform their respective roles and responsibilities.

If any of the Contractor's Key Personnel are unable to perform work as required by this clause or are removed following a direction of the Superintendent under clause 23, the Contractor must at the earliest opportunity provide appropriate personnel to replace the Key Personnel.

The Principal must consent in writing in advance to any replacement of the Contractor's Key Personnel.

Management Plans

Provision of Management Plans

The Contractor agrees to submit the Management Plans within 14 days after the Date of the Contract to the Superintendent for review and approval.

Following receipt of the Management Plans, the Superintendent will, within a reasonable time, either approve the Management Plans or return them to the Contractor with a short explanation as to why they were not approved, in which case the Contractor must amend the Management Plans and continue to submit them to the Superintendent until they are approved.

Each Management Plan which is approved by the Superintendent shall become the approved Management Plan.

Each approved Management Plan shall be a Contract document, together with all changes and amendments approved by the Superintendent under this clause.

The Contractor acknowledges and agrees that the approved Management Plans may require ongoing development, amendment and updating by the Contractor throughout the carrying out of the Works. The Contractor must update the approved Management Plans from time to time to take into account matters including:

          - any changes to the Site;

          - any changes in the Works; and

          - any changes in Legislative Requirements.

The Contractor agrees to promptly submit to the Superintendent each further version of a Management Plan as it is amended, developed or updated. Following approval by the Superintendent each Management Plan shall become the approved Management Plan.

The Contractor agrees that, notwithstanding any development, amendment or updated version of each Management Plan, the Contractor:

          - is not relieved of any liability or obligation under this Contract; or

          - is not entitled to any adjustment to the contract sum or an EOT to the Date for Practical Completion.

Management Plans Warranties

The Contractor warrants that the Management Plans will, at all times during the carrying out of the Works;

comply with this Contract; and

          - be implemented and maintained effectively by the Contractor in the carrying out of the Works.

Audits and Records

Archiving

The Contractor must:

          - comply and maintain a standard format of recording all project records acceptable or as directed by the Superintendent;

          - comply with any reasonable direction given by the Principal or the National Archives of Australia for the purpose of transferring a Commonwealth Record to the National Archives of Australia or providing the National Archives of Australia with full and free access to those records at the Principal’s cost; and

          - on or before the termination or the issue of the Final Certificate, deliver all Commonwealth Records in the Contractor’s possession or control to the Principal or, if directed by the Principal, to another person specified in writing by the Principal.

Commonwealth Records

Subject to the transfer of custody of Commonwealth Records in the performance of the Works, the Contractor must not arrange for, nor effect, a transfer of custody or ownership of any Commonwealth Record without the prior written approval of the National Archives of Australia.

The Contractor must ensure that the Principal has access at all times and in any manner to Commonwealth Records whilst they are in the Contractor’s possession or control.

Such access must be available to the Principal:

          - unconditionally;

          - without prior notice; and

          - at the Principal’s reasonable expense.

To facilitate the maintenance of Commonwealth Records and the Principal’s access to those records, the Contractor must, on a regular basis and no less than weekly, backup all of its records in electronic form relating to the Works under the Contract.

Ownership of Commonwealth Records

All Commonwealth Records and the Intellectual Property Rights in those Commonwealth Records transferred to the Contractor’s custody will remain the Principal’s property.

Administrative Record Keeping

The Contractor must maintain comprehensive records of any Variation. The records must include as a minimum:

          - origin of the request – including requestor and authoriser;

          - status of the Contractor’s progress in fulfilling the request;

          - where applicable, the price for fulfilment of the request; and

          - where applicable, details of the invoice containing the adjustment to the Contract Sum for fulfilment of the request.

The Contractor must retain all other records which are created, accessed or otherwise utilised for the performance of the Works under the Contract as reasonably specified by the Principal from time to time.

The Contractor must be able to provide to the Principal the records as being "immediately available" within 30 minutes after the records are requested unless another time period is agreed between the parties, where such agreement is not to be unreasonably withheld.

For records that have been archived by the Contractor, the Contractor must be able to make them available to the Principal, within 24 hours after the records are requested, unless another time period is agreed between the parties, which agreement is not to be unreasonably withheld and provided that the Principal has been able to reasonably identify the records.

Definition of Commonwealth Record

'Commonwealth Record' has the same meaning as in the Archives Act 1983 (Cth).

Digital Continuity 2020 Policy

The Contractor must comply with and follow any of the Principal’s reasonable directions which are relevant to any applicable Legislative Requirements or policies relating to archival and information management requirements. This may include directions in relation to the ICT requirement under the Digital Continuity 2020 Policy (issued under the Archives Act 1983 (Cth)) to ensure all business systems have appropriate information management functionality

Audits

The Contractor agrees that the Principal, Superintendent or another nominated person or entity, may:

          - audit the Contractor for compliance with this Contract, including records and financial accounts;

          - access the Site and any area occupied by the Contractor where the Works are being carried out or where any documentation relevant to the Works are being performed is held; and

          - inspect and take copies of any materials relevant to the Works.

The Contractor must participate in audits at the frequency and in relation to the matters specified by the Principal or the Superintendent.

The Auditor-General and the Privacy Commissioner are persons authorised for the purposes of this clause 52.

This clause 52 does not detract from the statutory powers of the Auditor-General or the Privacy Commissioner.

Each party to an audit must bear its own costs of the audit.

Records

The Contractor shall:

keep and shall require its subcontractors to keep adequate books and records, in accordance with Australian accounting standards, in sufficient detail to enable the amounts payable by the Principal under the Contract to be determined; and

retain and require its subcontractors to retain for a period of seven years after termination of the Contract or the issue of the Final Certficate, all books and records relating to the Works.

Access to Documents

In this clause 53, document and Commonwealth contract have the same meaning as in the Freedom of Information Act 1982 (Cth).

The Contractor acknowledges that this Contract is a Commonwealth Contract. Where the Principal has received a request for access to a document created by, or in the possession of, the Contractor or any subcontractor that relates to the performance of this Contract (and not to the entry into the Contract), the Principal may, at any time by written notice, require the Contractor to provide the document to the Principal and the Contractor must, at no additional cost to the Principal, promptly comply with the notice.

The Contractor must include in any subcontract relating to the performance of this Contract provisions that will enable the Contractor to comply with its obligations under this clause 53.

Privacy

The Contractor must:

comply with its obligations under the Privacy Act;

comply with the Australian Privacy Principles (as defined in the Privacy Act) when doing any act or engaging in any practice for the purposes of this Contract, as if it were an agency as defined in the Privacy Act;

use Personal Information (as defined in the Privacy Act) received, created or held by the Contractor for the purposes of, under, arising out of or in connection with this Contract only for the purposes of fulfilling its obligations under this Contract;

not disclose Personal Information received, created or held by the Contractor for the purposes of, under, arising out of or in connection with this Contract without the prior written approval of the Principal;

not collect, transfer, store or otherwise use Personal Information received, created or held by the Contractor for the purposes of, under, arising out of or in connection with this Contract outside Australia, or allow parties outside Australia to have access to it, without the prior written approval of the Principal;

co-operate with demands or inquiries made by the Federal Privacy Commissioner or the Principal in relation to the management of Personal Information in connection with this Contract;

ensure that any person whom the Contractor allows to access Personal Information which is received, created or held by the Contractor for the purposes of, under, arising out of or in connection with this Contract is made aware of, and undertakes in writing to observe, the Australian Privacy Principles, as if the person was an agency as defined in the Privacy Act;

comply with policy guidelines laid down by the Commonwealth or issued by the Federal Privacy Commissioner from time to time relating to Personal Information;

ensure that records (as defined in the Privacy Act) containing Personal Information received, created or held by the Contractor for the purposes of, under, arising out of or in connection with this Contract are, at the expiration or earlier termination of this Contract, at the Principal’s election, to be either returned to the Commonwealth or deleted or destroyed in the presence of a person duly authorised by the Principal to oversee such deletion or destruction;

agree to the naming or other identification of the Contractor in reports by the Federal Privacy Commissioner;

ensure that any subcontract made in connection with this Contract contains enforceable obligations requiring the subcontractor to comply with the Contractor's obligations arising out of clause 54 of the Contract, as if the subcontractor were the Contractor,

enforce the obligations referred to in subparagraph (xi) in accordance with such directions as the Principal may give;

not use Personal Information collected by the Contractor for the purposes of, under, arising out of, or in connection with the Contract for, or in any way relating to, any direct marketing purpose; and

indemnify the Principal in respect of all costs, expenses, losses, damages or liabilities suffered or incurred by the Principal arising out of or in connection with:

a breach of the obligations of the Contractor under this clause 54 of the Contract;

a breach of a subcontractor’s obligations under a subcontract as contemplated by subparagraph (xi);

the misuse of Personal Information held for the purposes of, under, arising out of or in connection with this Contract by the Contractor or a subcontractor; or

              - the disclosure of Personal Information held for the purposes of, under, arising out of or in connection with this Contract by the Contractor or a subcontractor in breach of an obligation of confidence.

For the purposes of paragraph (xiv) above, costs, expenses, losses, damages or liabilities includes any compensation paid to a person by or on behalf of the Principal to settle a complaint arising out of or in connection with a breach of this clause 54 by the Contractor.

The Contractor must immediately notify the Principal in writing if the Contractor:

becomes aware of a breach of the obligations under this clause 54 by itself or by a subcontractor;

becomes aware of a breach of a subcontractor's obligations under a subcontract as contemplated by paragraph (xi);

becomes aware that a disclosure of Personal Information may be required by law; or

is approached or contacted by or becomes aware that a subcontractor has been approached or contacted by the Federal Privacy Commissioner or by a person claiming that their privacy has been interfered with.

The Contractor acknowledges that, in addition to the requirements of clause 54, the Contractor may also be obliged to comply with other obligations in relation to the handling of Personal Information, including State and Territory legislation.

In this clause 54:

'Australian Privacy Principle' has the meaning given in the Privacy Act;

'Personal Information' has the meaning given in the Privacy Act;

'Privacy Act' means the Privacy Act 1988 (Cth); and

received includes collected.

Representations Made as Part of Tender

Except to the extent of any inconsistent with this Contract, the Contractor must comply with all representations made as part of its tender and the subsequent meetings and correspondence for the WUC.

Representations, Sanctions, Counter Terrorism and Anti-terrorism

The Contractor must comply with its obligations (if any) under Part 4 of the Charter of the United Nations Act 1945 (Cth) and the Charter of the United Nations (Dealing with Assets) Regulations 2008 (Cth).

The Contractor must comply with all applicable Legislative Requirements dealing with the supply and/or export of goods, services and information to foreign nationals or institutions, including under the Customs Act 1901 (Cth) and the Weapons of Mass Destruction (Prevention of Proliferation) Act 1995 (Cth).

The Contractor acknowledges that it is an offence to knowingly make any funds or assets available to a person or organisation on the list of persons and entities designated as terrorist, available at https://www.dfat.gov.au/international-relations/security/sanctions/Pages/consolidated-list ('Consolidated List'). The Contractor must not deal with any such person or organisation.

The Contractor must, and must ensure that its agents, subcontractors, and employees:

ensure that individuals or organisations involved in implementing this Contract are in no way linked, directly or indirectly, to organisations and individuals associated with terrorism, including ‘terrorist organisations' as defined in Division 102 of the Criminal Code Act 1995 (Cth) and listed in regulations made under that Act and regulations made under the Charter of the United Nations Act 1945 (Cth); and

ensure that payments provided by the Principal are not used in any way to provide direct or indirect support or resources to organisations and individuals associated with terrorism.

in carrying out its obligations under this Contract, comply with laws in relation to sanctions including the Charter of the United Nations Act 1945 (Cth) and regulations made under that Act; the Autonomous Sanctions Act 2011 (Cth) and regulations made under that Act; and

ensure that payments provided by the Principal are not used in any way to provide direct or indirect support or resources to organisation and individuals for whom Australia has imposed sanctions under the Charter of the United Nations Act 1945 (Cth) and regulations made under that Act or the Autonomous Sanctions Act 2011 (Cth) and regulations made under that Act; and

inform the Principal, if during the term of this Contract, it discovers any link whatsoever with any organisation or individual listed in or the World Bank List or a Relevant List including DFAT's Consolidated List.

If the Contractor, its personnel or subcontractors become aware or should have reasonably become aware that funds or resources have directly or indirectly been provided to organisations or individuals associated with terrorism, the Contractor must inform the Principal immediately. Any failure by the Contractor to provide such notice shall be a "substantial breach" for the purposes of subclause 39.2 of the Contract

Prohibited Dealings

The Contractor must ensure that funds provided under this Contract (whether through a subcontract or not) are not used in any way to provide or facilitate direct or indirect support, resources or assets to individuals, entities or organisations:

listed on the World Bank List or any similar List;

listed on the Consolidated List;

listed on the Australian Government list of terrorist organisations at https://www.nationalsecurity.gov.au/what-australia-is-doing/terrorist-organisations/listed-terrorist-organisations; or

directly or indirectly engaged in, preparing, planning, assisting in or fostering the doing of a terrorist act.

The Contractor warrant that neither the Contractor nor its Key Personnel will make or cause to be made, receive or seek to receive any offer, gift or payment, or benefit of any kind, which could be construed as an illegal or corrupt act, either directly or indirectly to any Party, in relation to this Contract.

A breach of this clause 57 will be a "substantial breach" for the purposes of subclause 39.2 of the Contract.

Fraud

The Contractor must not, and must ensure that that its agents, subcontractors, and employees, including key personnel do not, engage in any fraud and must prevent and detect fraud, including fraud by its personnel.

Within one month of the Date of the Contract, the Contractor must conduct a fraud risk assessment and produce a fraud control strategy in compliance with the Commonwealth Fraud Control Framework available at https://www.apsc.gov.au/initiatives-and-programs/workforce-information/research-analysis-and-publications/state-service/state-service-report-2023-24/integrity/commonwealth-fraud-and-corruption-control-framework. The risk assessment and strategy must contain appropriate fraud prevention, detection, investigation and reporting processes and procedures.

The Contractor is responsible for preventing and detecting fraud including fraud within those functions performed by a subcontractor relating to the performance of the Works under this Contract. The Contractor must ensure that its agents, subcontractors, and employees, including Key Personnel, are responsible and accountable to the Contractor for preventing and reporting any fraud as part of their routine responsibilities. The Contractor must ensure that Personnel who are not employed by the Contractor report fraud to the Contractor within 7 days.

If the Contractor, its agents, subcontractors, and employees, including Key Personnel becomes aware of a fraud, it must report the matter to the Principal in writing within 7 days. The written report to the Principal must be signed by a Contractor authorised person and must include the following (where known):

the name of the Contract under which the Principal’s payment(s) is being provided;

name of any personnel (including any subcontractors) involved;

the allegation(s), including a chronological account of the facts giving rise to the allegation(s);

the names of the suspected offender(s) (where known);

details of witnesses;

copies of relevant documents;

references to any relevant legislation;

a nominated contact officer;

any other relevant information (for example, political sensitivities, any other party or agency that has been informed, involved or that can assist with investigations); and

the current status of any inquiries commenced by the Contractor.

If a report has been made in accordance with this clause 58, the Contractor must respond within seven days to any further requests for information the Principal may make.

If the Contractor, its agents, subcontractors, and employees, including Key Personnel becomes aware of a fraud, the Contractor must, in consultation with Principal, develop and implement a strategy to investigate the fraud based on the principles set out in the Australian Government Investigations Standards.

The Contractor must investigate the fraud at the Contractor’s cost and in accordance with any directions or standards required by Principal. Whether the Contractor conducts an investigation or appoints an investigator to conduct an investigation, the person conducting the investigation must possess the minimum qualifications specified in the Australian Government Investigation Standards or an equivalent agreed to by the Principal.

The Principal reserves the right to appoint its own investigator, conduct its own investigation or report fraud to the appropriate law enforcement agencies or any other person or entity the Principal deems appropriate for investigation. If the Principal exercises these rights, the Contractor must provide all reasonable assistance that may be required at its sole expense.

After the investigation is finished, if a suspected offender has been identified or at the direction of the Director of the Principal’s Customer Fraud Control Section, the Contractor must promptly report the fraud to the local police and any other appropriate law enforcement agency where the incident occurred, unless the Director of Customer’s Fraud Section agrees otherwise in writing.

If the investigation finds the Contractor or employees including Key Personnel have engaged in fraud, the Contractor, in consultation with the Principal, must take all action necessary to recover, replace or return to the Principal any misappropriated funds or property (including paying to the Principal the full value of misappropriated funds and returning or replacing misappropriated or damaged property).

If the investigation finds that a person other than the Contractor or employee including Key Personnel has engaged in fraud, the Contractor must, at the Contractor’s cost, take all reasonable action to recover any Principal funds or Principal-funded property acquired or distributed through the fraud, including taking recovery action in accordance with recovery procedures (including civil litigation) available in the relevant country.

The Contractor must keep the Principal informed, in writing, on a monthly basis, of the progress of its efforts to recover the Principal's payments or Principal-funded property, including any recovery action.

If the Contractor considers that all reasonable action has been taken to recover the Principal’s payments or the Principal's-funded property and recovery has not been achieved or recovery has only been achieved in part, the Contractor may seek approval from the Principal that, no further recovery action be taken.

If an investigation finds that the Contractor or employees including Key Personnel have engaged in fraud, or if the Principal discovers that a fraud has not been reported to the Principal, the Principal reserves the right to:

terminate this Contract by giving the Contractor notice in writing specifying the date on which the termination will take effect, in which case the consequences of the termination will be as set out in subclause 39.10; and

not enter into any further agreements with the Contractor until such time as the Principal is satisfied that any recommended changes to the Contractor’s management and procedures have been made in order to prevent any further fraud from occurring and to ensure timely reporting of fraud to the Principal.

Without limitation to any of the Principal’s rights pursuant to subclause 39.10 (Termination), if the Contractor fails to comply with its obligations under this clause 58 with respect to a fraud, the Principal may give the Contractor a written notice which specifies:

the obligation/s with which the Contractor has not complied;

the action that the Contractor must take to rectify the failure; and

the date by which the contractor must rectify the failure.

If the Contractor does not comply with a notice issued, the Principal reserves the right to:

terminate this Contract in accordance with subclause 39.10 (Termination); and/or

withhold payments (or parts of payments) due to the Contractor, until the Contractor has complied with the notice.

This clause 58 survives the termination or expiration of this Contract, including with respect to any Fraud relating to the performance of this Contract, which is not detected until after this Contract has been terminated or has expired.

Anti-Corruption

The Contractor warrants that, to the best of the Contractor’s knowledge as at the Date of the Contract, no money or other consideration of any kind paid or payable under this Contract or by separate agreement is, has been or will be used for unlawful purposes, including purposes violating anti-corruption legislation, including making or causing to be made payments to any employee of either Party or anyone acting on their behalf to assist in obtaining or retaining business to any person, or securing any improper advantage.

The Contractor warrants that neither it nor its agents, subcontractors, and employees, including Key Personnel will make or cause to be made, receive or seek to receive any offer, gift or payment, or benefit of any kind, which could be construed as an illegal or corrupt act, either directly or indirectly to any party, in relation to the execution of this Contract.

Any breach of this clause 59 (Anti-Corruption) will entitle the Principal to issue a notice under subclause 39.10 (Termination) to terminate this Contract immediately.

Child Protection

The Contractor (and any Subcontractor) must comply with all relevant Australian and local legislation and labour laws in relation to child labour.

The Contractor must also comply with, and ensure that its officers, employees, subcontractors and agents comply with, DFAT's ‘Child Protection Policy', accessible on the DFAT website at: www.dfat.qov.au.

If any part of the activities carried out by the Contractor under the Contract involves the Contractor employing or engaging a person (whether as an officer, employee, agent, subcontractor, or volunteer) that is required by any law in the State or Territory in which the Works is to be conducted to have a working with children check to undertake such activities or any part of such activities, the Contractor agrees:

without limiting its other obligations under the Contract, to comply with all State, Territory or Commonwealth law relating to the employment or engagement of people who work or volunteer with children in relation to such activities, including mandatory reporting and working with children checks however described; and

if requested, provide the Principal at the Contractor's cost, a statement of compliance with this clause, in such form as may be specified by the Principal.

When child safety obligations may be relevant to a subcontract made in connection with the Contract, the Contractor must ensure that any such subcontract entered into by the Contractor for the purposes of fulfilling the Contractor's obligations under the Contract imposes on the subcontractor the same obligations regarding child protection that the Contractor has under the Contract. Each subcontract must also require the same obligations (where relevant) to be included by the subcontractor in any secondary subcontracts.

Preventing sexual exploitation, abuse and harassment (PSEAH)

When undertaking the Works, the Contractor must comply, and must ensure that its contractors, subcontractors, agents and personnel comply, with DFAT’s Preventing Sexual Exploitation, Abuse and Harassment (PSEAH) Policy, including the reporting obligations, accessible at http://www.dfat.gov.au/pseah.

The Principal may conduct a review of the Contractor's compliance with DFAT’s PSEAH Policy. The Principal will give reasonable notice (at least 14 calendar days) to the Contractor and the Contractor must participate co-operatively in any such reviews.

If the Principal finds that the Contractor has failed to comply with DFAT’s PSEAH Policy, the Contractor must promptly, and at the cost of the Contractor, take such actions as are required to ensure compliance standards in the PSEAH Policy.

In reporting to the Principal, as required under this clause 61, the Contractor must comply with the Privacy Act 1988 (Cth) and the privacy provisions in the DFAT SEAH Incident Notification Form, available on DFAT’s website.

Modern Slavery and Human Trafficking

The Contractor must take reasonable steps to identify, assess and address risks of Modern Slavery practices in the operations and supply chains used in the provision of the Works.

If at any time the Contractor becomes aware of Modern Slavery practices in the operations and supply chains used in the performance of the Contract, the Contractor must as soon as reasonably practicable take all reasonable action to address or remove these practices, including where relevant by addressing any practices of other entities in its supply chains. Incidents and the process taken to identify and address risk (form of a Modern Slavery risk management plan) must be reported to the Principal as soon as practical by contacting the Superintendent.

For the purposes of this clause 61, 'Modern Slavery' has the meaning given in the Modern Slavery Act 2018 (Cth).

Environmental Requirements

The Contractor must ensure that in carrying out the Works:

it complies with all Legislative Requirements, the Principal's requirements and other requirements of the Contract for the protection of the environment;

it complies with all directions of the Principal or the Superintendent in relation to the environment; and

it immediately notifies the Superintendent of:

any non-compliance with the requirements of this clause 63;

any breach of any law for the protection of the environment; or

the receipt of any notice, order or communication received from any relevant authority for the protection of the environment.

Pandemic Relief Event

If the Contractor considers that there has been a Pandemic Relief Event, it must promptly notify the Superintendent in writing, providing details of the Pandemic Relief Event, and follow the instructions given by the Superintendent.

Where the Superintendent has determined a Pandemic Relief Event has occurred, the Contractor and the Superintendent are to agree the costs incurred by the Contractor because of the Pandemic Relief Event, excluding delay costs (if any) which are to be compensated under subclause 34.9 of the Contract, and if unable to agree, the Superintendent is to determine the costs.

To the extent permitted by Legislative Requirements, the Contractor will not be entitled to make (nor will the Principal be liable upon) any Claim arising out of or in connection with a Pandemic Relief Event or any instruction under paragraph (a), other than under this clause 64.

The Superintendent will reduce any entitlement the Contractor would have otherwise had under paragraph (b) to the extent that the Contractor has failed to take all reasonable steps to mitigate the costs referred to in paragraph (b).

For the purposes of this clause 64:

'Pandemic' means the disease known as Coronavirus (COVID-19) which was characterised to be a pandemic by the World Health Organisation on 11 March 2020; and

'Pandemic Relief Event' means a disruption which has an adverse effect on the supply of labour, equipment, materials or services required for the carrying out of the WUC caused as a direct result of the Pandemic, provided that the adverse effect is one which the Contractor could not have avoided or overcome by the taking of all reasonable steps (but without the need to expend additional costs).

Commonwealth Supplier Code of Conduct

The Contractor must comply with, and ensure that its officers, employees, agents and Subcontractors comply with, the Code in connection with the performance of the Contract.

The Contractor must:

periodically monitor and assess its, and its officers’, employees’, and agents’ compliance with the Code; and

on request from the Principal, promptly provide information regarding:

the policies, frameworks, or systems it has established to monitor and assess compliance with the Code; and

the Contractor’s compliance with paragraph (a) above.

The Contractor must immediately notify the Principal in writing upon becoming aware of any breach of paragraph (a) above. The notice must include a summary of the breach, the date that the breach occurred and details of the personnel involved.

Where the Principal identifies a possible breach of paragraph (a) above, it may notify the Contractor in writing, and the Contractor must, within 3 days of receiving the notice, either:

where the Contractor considers a breach has not occurred – advise the Principal that there has not been a breach and provide information supporting that determination; or

where the Contractor considers that a breach has occurred – notify the Principal under paragraph (b) above and otherwise comply with its obligations under this clause 65.

A failure by the Contractor to comply with its obligations under any part of this clause 65 will be a breach of the Contract.

Nothing in this clause or the Code limits, reduces or derogates from the Contractor’s other obligations under the Contract. The Principal’s rights under this clause are in addition to and do not otherwise limit any other rights the Principal may have under the Contract. The performance by the Contractor of its obligations under this clause will be at no additional cost to the Principal.

The Contractor acknowledges that the Principal may take the Contractor’s compliance with the Code into account in any registration of interest process, tender process or similar procurement process in connection with any other Commonwealth project.

For the purposes of this clause, 'Code' means the Commonwealth Supplier Code of Conduct dated 1 July 2024 accessible from the following link: https://www.finance.gov.au/government/procurement/commonwealth-supplier-code-conduct/commonwealth-supplier-code-conduct (as amended from time to time).

Notification of Significant Events

The Contractor must immediately issue the Principal a notice on becoming aware of a Significant Event, summarising the Significant Event (including the date on which it occurred and specifying whether the personnel involved were involved in the Works).

The Principal may notify the Contractor in writing that an event is to be considered a Significant Event for the purposes of this clause, and where this occurs the Contractor must issue a notice under paragraph (a) above in relation to the event within 5 days of being notified by the Principal.

If requested by the Principal, the Contractor must provide the Principal with any additional information regarding the Significant Event within 5 days of the request or prepare a draft remediation plan and submit that draft plan to the Principal for approval within 14 days of the request.

A draft remediation plan prepared by the Contractor under paragraph (c) above must include any such details as reasonably requested by the Principal.

The Principal will review the draft remediation plan and either approve the draft remediation plan or provide the Contractor with the details of any changes that are required. The Contractor must make any changes to the draft remediation plan reasonably requested by the Principal and resubmit the draft remediation plan to the Principal for approval within 5 days of the request.

Without limiting its other obligations under the Contract, the Contractor must comply with the remediation plan as approved by the Principal, and provide reports and other information about the Contractor’s progress in implementing the remediation plan as reasonably requested by the Principal.

A failure by the Contractor to comply with its obligations under this clause will be a breach of the Contract. The Principal’s rights under this clause are in addition to and do not otherwise limit any other rights the Principal may have under the Contract. The performance by the Contractor of its obligations under this clause will be at no additional cost to the Principal.

For the purposes of this clause 66, 'Significant Event' means:

any adverse comments or findings made by a court, commission, tribunal or other statutory or professional body regarding the conduct or performance of the Contractor or its officers, employees, agents or subcontractors that impacts or could be reasonably perceived to impact on their professional capacity, capability, fitness or reputation; or

any other significant matters, including the commencement of legal, regulatory or disciplinary action involving the Contractor or its officers, employees, agents or subcontractors, that may adversely impact on compliance with DFAT or Commonwealth policy, legislation or DFAT or the Commonwealth’s reputation.

Ethical Conduct

The Contractor acknowledges and agrees that the Principal observes high ethical standards in the conduct of its activities, and the Principal is relying on the Contractor observe high ethical standards in the performance of its obligations and duties in the execution of the Works (as reasonably determined by the Superintendent).

The Contractor must ensure that each of its officers, employees and subcontractors observe similar standards of ethical conduct.

Without limiting the generality of the previous paragraph, the Contractor must not engage in (and will use its best endeavours to ensure that its employees and subcontractor’s does not engage in):

conduct that is misleading, fraudulent or deceptive;

conduct that is illegal under the laws of Australia or Papua New Guinea;

conduct that amounts to bribery; or

conduct that amounts to terrorism or that supports or assists terrorism.

Workplace Gender Equality

The Contractor must, where the Contractor is a 'relevant employer' for the purposes of the Workplace Gender Equality Act 2012 (Cth) ('WGE Act'):

comply with the Contractor’s obligations, if any, under the WGE Act; and

not enter into a subcontract with an entity named in a report tabled in the Australian Parliament by the Director of the Workplace Gender Equality Agency as a supplier that has not complied with the WGE Act.

If the Contractor is a 'relevant employer' under the WGE Act and become[s] non-compliant with the WGE Act, the Contractor must notify the Superintendent as soon as reasonably practical.

The Contractor must provide a current letter of compliance from the Workplace Gender Equality Agency within 18 Months from the Date of the Contract and following this, annually, to the Superintendent.

Compliance with the WGE Act does not relieve the Contractor from the Contractor’s responsibility to comply with the Contractor’s other obligations under this Contract.

Applicable Laws and Polices

Without limiting any other provision of this Contract, the Contractor must (to the fullest extent possible, regardless of its legal application) comply with the following legislation of the Commonwealth of Australia ('Commonwealth') and policies in connection with this Contract and when performing the Works under the Contract, as if all the Works under the Contract were performed, and this Contract were being performed for the Commonwealth in the Australian Capital Territory:

Anti-Money Laundering and Counter-Terrorism Financing Act 2006 (Cth);

Archives Act 1993 (Cth);

Attorney General's 'Legal Services Directions' as issued by the Attorney General in accordance with the Judiciary Act 1903 (Cth);

Auditor-General Act 1997 (Cth);

Australian Human Rights Commission Act 1986 (Cth);

Autonomous Sanctions Act 2011 (Cth);

Autonomous Sanctions Regulations 2011 (Cth);

Charter of the United Nations Act 1945 (Cth);

Charter of the United Nations (Dealing with Assets) Regulations 2008 (Cth);

Commonwealth Fraud Control Framework 2017;

Commonwealth Procurement Rules;

Commonwealth Tax Law;

Competition and Consumer Act 2010 (Cth);

Crimes Act 1914 (Cth);

Criminal Code Act 1995 (Cth) (Criminal Code) (including but not limited to Division 70 and Division 137.1 of the Criminal Code);

Customs Act 1901 (Cth);

Cybercrime Act 2001 (Cth);

Disability Discrimination Act 1992 (Cth) and the Disability Standards for Education 2005;

Education Services for Overseas Students Act 2000 (Cth) and National Code of Practice for Providers of Education and Training to Overseas Students 2018;

Environment Protection and Biodiversity Conservation Act 1999 (Cth);

Fair Work Act 2009 (Cth);

Fair Work Regulations 2009 (Cth);

Freedom of Information Act 1982 (Cth);

Government Procurement (Judicial Review) Act 2018 (Cth);

Migration Act 1958 (Cth);

Modern Slavery Act 2018 (Cth);

National Anti-Corruption Commission Act 2022 (Cth);

Ombudsman Act 1976 (Cth);

Payment Times Reporting Act 2020 (Cth);

Payment Times Procurement Connected Policy;

Privacy Act 1988 (Cth);

Public Governance, Performance and Accountability Act 2013 (Cth);

Public Interest Disclosure Act 2013 (Cth);

Public Service Act 1999 (Cth);

Racial Discrimination Act 1975 (Cth);

Safety Rehabilitation and Compensation Act 1968 (Cth);

Sex Discrimination Act 1984 (Cth);

Weapons of Mass Destruction (Prevention of Proliferation) Act 1995 (Cth);

Workplace Gender Equality Act 2012 (Cth) (WGE Act);

Work Health and Safety Act 2011 (Cth); and

any other Legislative Requirement or policy notified to the Contractor in writing by the Principal from time to time.

|  | ANNEXURE to the Australian Standard General Conditions of Contract for Design and Construct |  |  |  |  | Part A |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | This Annexure shall be completed and issued as part of the tender documents and, subject to any amendments to be incorporated into the Contract, is to be attached to the General Conditions of Contract and shall be read as part of the Contract. |  |  |  |  |  |  |  |  |  |
|  | Item |  |  |  |  |  |  |  |  |  |
|  |  |  | # Principal (clause 1) |  | Commonwealth of Australia represented by the Overseas Property Office of the Department of Foreign Affairs and Trade (ABN 47 065 634 525) |  |  |  |  |  |
|  |  |  | # Principal's address |  | R G Casey Building, John McEwen Crescent, Barton, 0221 ACT Phone: +61 2 6261 1111 Email: aopoprojects@dfat.gov.au |  |  |  |  |  |
|  |  |  | Contractor (clause 1) |  | [#Insert] |  |  |  |  |  |
|  |  |  | # Contractor's address |  | [#Insert] Phone: [#Insert] Email: [#Insert] |  |  |  |  |  |
|  |  |  | # Superintendent (clause 1) |  | [#Insert] |  |  |  |  |  |
|  |  |  | # Superintendent's address |  | [#Insert] Phone: [#Insert] Email: [#Insert] |  |  |  |  |  |
|  | # 6A. |  | # Stages (Clause 1) |  | As described in detail in the Principal's Project Requirements: House No.; Street; Accommodation Type; Number of Bedrooms. Stage 2; 35; 6th Street; Stand-alone townhouse; 3. 36; 6th Street; Stand-alone townhouse; 4. 37; 6th Street; Stand-alone townhouse; 4. 38; 6th Street; Stand-alone townhouse; 4. 39; Access; Stand-alone townhouse; 4. Stage 3; 29; 4th Street; Apartment; 4. 30; 4th Street; Apartment; 3. 31; 4th Street; Apartment; 3. 32; 5th Street; Apartment; 4. 33; 5th Street; Apartment; 3. 34; 5th Street; Apartment; 3. Stage 4; 23; 3rd Street; Apartment; 3. 24; 3rd Street; Apartment; 4. 25; 4th Street; Apartment; 4. 26; 4th Street; Apartment; 3. 27; 4th Street; Apartment; 4. 28; 4th Street; Apartment; 4. Stage 5; 13; 2nd Street; Stand-alone townhouse; 3. 14; 2nd Street; Stand-alone townhouse; 4. 15; 2nd Street; Stand-alone townhouse; 4. 16; 2nd Street; Stand-alone townhouse; 3. Stage 6; 17; 2nd Street; Apartment; 4. 18; 2nd Street; Apartment; 3. 19; 2nd Street; Apartment; 3. 20; 2nd Street; Apartment; 4. 21; 2nd Street; Apartment; 3. 22; 2nd Street; Apartment; 3. Stage 7; 1; 1st Street; Stand-alone townhouse; 4. 2; 1st Street; Stand-alone townhouse; 4. 3; 1st Street; Stand-alone townhouse; 4. 4; 1st Street; Stand-alone townhouse; 4. 5; 1st Street; Duplex; 4. 6; 1st Street; Duplex; 4. Stage 8; 7; 1st Street; Stand-alone townhouse; 4. 8; 1st Street; Stand-alone townhouse; 4. 9; 1st Street; Duplex; 4. 10; 1st Street; Duplex; 4. 11; 1st Street; Duplex; 4. 12; 1st Street; Duplex; 4. |
|  | # 6B. |  | # Date for Delivery Phase Approval (Clause) |  | Stage; Date for Practical Completion. Stage 2; 6 November 2026. Stage 3; 2 June 2027. Stage 4; 6 December 2027. Stage 5; 22 June 2028. Stage 6; 03 January 2029. Stage 7; 4 July 2029. Stage 8; 16 January 2029. |
| † |  |  | # Date for Practical Completion (clause 1) |  | Stage; Date for Practical Completion. Stage 2; 2 April 2027. Stage 3; 15 October 2027. Stage 4; 28 April 2028. Stage 5; 27 October 2028. Stage 6; 11 May 2029. Stage 7; 9 Nov 2029. Stage 8; 17 May 2030. |
|  | # 7A. |  | # Provisional Allowance (Cost) (clause 1) |  | [#Insert] |  |  |  |  |  |
|  | # 7B. |  | # Provisional Allowance (Time) (clause 1) |  | [#Insert] |  |  |  |  |  |
|  |  |  | # Governing law (clause 1(h)) |  | Australian Capital Territory |  |  |  |  |  |
|  | 8A. |  | Host Nation (clause 1) |  | Papua New Guinea |  |  |  |  |  |
|  |  |  | # Currency (clause 1(g)) |  | PNG Kina |  |  |  |  |  |
|  |  |  | # Not used |  |  |  |  |  |  |  |
|  |  |  | # Preliminary design (clause 1) |  | As set out in the Principal's Project Requirements |  |  |  |  |  |
|  |  |  | # Not used |  |  |  |  |  |  |  |
|  |  |  | Not used |  |  |  |  |  |  |  |
| † |  |  | # Contractor's Security |  |  |  |  |  |  |  |
|  |  |  | (a) Form (clause 5) |  | unconditional bank guarantee |  |  |  |  |  |
|  |  |  | (b) Amount or maximum percentage of Contract Sum (clause 5) |  | 5% of the Contract Sum (Stage) made up of 2 bank guarantees of 2.5% of the Contract Sum |  |  |  |  |  |
|  |  |  | (d) Time for provision (clause 7) |  | within 28 days after the Delivery Phase Approval for each Stage |  |  |  |  |  |
|  |  |  | (e) Additional Security for unfixed plant and materials (subclauses 5.4 and 37.3) |  | 30% of the value of the relevant unfixed plant and materials. |  |  |  |  |  |
|  |  |  | (f) Contractor's Security upon Certificate of Practical Completion of each Stage is reduced by (subclause 5.4) |  | 50% of amount held |  |  |  |  |  |
| † |  |  | # Not Used |  |  |  |  |  |  |  |
|  |  |  | # Principal-supplied documents (subclause 8.2) |  | Document |  |  | No. of copies |  |  |
|  |  |  |  |  | 1. Principal’s Project Requirements |  |  | As reasonably requested by the Contractor |  |  |
|  |  |  | # Documents, numbers of copies, and the times or stages at which they are to be supplied by the Contractor (subclause 8.3) |  |  |  |  |  |  |  |
|  |  |  | Document; No. of copies; Time/stage. Due diligence Report and dilapidation Report,; 1 electronic copy & 1 printed and bound copy; As directed by the Superintendent. As Built drawings, asset register and O&M documentation; 1 electronic copy and 1 printed and bound copy; As directed by the Superintendent. |
|  |  |  | # Time for Superintendent's review of Design Documents (subclause 8.3) |  | 14 days |  |  |  |  |  |
|  |  |  | # Not used |  |  |  |  |  |  |  |
|  |  |  | # Not used |  |  |  |  |  |  |  |
|  |  |  | # Not used |  |  |  |  |  |  |  |
|  |  |  | # Legislative Requirement |  |  |  |  |  |  |  |
|  |  |  | (a) Those excepted (subclause 11.1) |  | None |  |  |  |  |  |
|  |  |  | (b) Identified WUC (subclause 11.2(b)(i)(B)) |  | None |  |  |  |  |  |
|  |  |  | # Insurance of the Works (clause 16A) |  |  |  |  |  |  |  |
|  |  |  | (a) Provision for demolition and removal of debris |  | 5% of the Contract Sum (Aggregate) |  |  |  |  |  |
|  |  |  | # Professional indemnity insurance (clause 16B and subclause 9.2(d)) |  |  |  |  |  |  |  |
|  |  |  | (a) Levels of cover of Contractor's professional indemnity insurance shall be not less than |  | K50,000,000 |  |  |  |  |  |
|  |  |  | (b) Period for which Contractor's professional indemnity insurance shall be maintained after issue of the Final Certificate |  | 6 years |  |  |  |  |  |
|  |  |  | (c) Categories of Consultants and levels of cover of Consultants' professional indemnity insurance |  | Category |  |  |  | Levels of cover |  |
|  |  |  |  |  | Professional Legal Liability for any claim or claims first made against the Insured during the period of cover and which is notified in writing to the Insurer, for breach of Professional Duty in the conduct of professional business practice carried on by the Insured by reason of negligent act, error, omission committed or alleged to have been committed by the Insured. |  |  |  | K50,000,000 |  |
|  |  |  | (d) Period for which each Consultant's professional indemnity insurance shall be maintained after issue of the Final Certificate |  | 6 years |  |  |  |  |  |
|  |  |  | # Public liability insurance (clause 17) |  |  |  |  |  |  |  |
|  |  |  | (a) Amount per occurrence shall be not less than |  | [K20,000,000] per occurrence and unlimited in the aggregate |  |  |  |  |  |
|  |  |  | # (a) Time for giving access (subclause 24.1) |  | 14 days. |  |  |  |  |  |
|  |  |  | # The information, materials, documents or instructions and the times by, or periods within which they are to be given to the Contractor (clause 32) |  | Documents or instructions |  |  |  |  | Times/Periods |
|  |  |  |  |  | 1. Computer-Aided Drawings |  |  |  |  | To be inserted within 3 business days of the Date of the Contract |
|  |  |  | # Not Used |  | # |  |  |  |  |  |
|  |  |  | # Liquidated damages, rate (subclause 34.7) |  | - For delay to Practical Completion for Stage 2: 3,800 PGK per day. - For delay to Practical Completion for Stage 3: 3,800 PGK per day. - For delay to Practical Completion for Stage 4: 3,800 PGK per day. - For delay to Practical Completion for Stage 5: 3,800 PGK per day. - For delay to Practical Completion for Stage 6: 3,800 PGK per day. - For delay to Practical Completion for Stage 7: 3,800 PGK per day. - For delay to Practical Completion for Stage 8: 3,800 PGK per day. |  |  |  |  |  |
|  |  |  | # Delay Costs daily cap # (subclause 34.9) |  | 10,984.74 per day. |  |  |  |  |  |
|  |  |  | # Not used |  |  |  |  |  |  |  |
|  |  |  | # Defects Liability Period (clause 35) |  | 12 months |  |  |  |  |  |
|  |  |  | # Progress Claims (subclause 37.1) |  |  |  |  |  |  |  |
|  |  |  | (a) Times for progress claims |  | The 20th day of each month for WUC done to the last day of that month |  |  |  |  |  |
|  |  |  | # Unfixed plant and materials for which payment claims may be made (subclause 37.3) |  |  |  |  |  |  |  |
|  |  |  | # Interest rate on overdue payments (subclause 37.5) |  | The Reserve Bank of Australia cash rate as at the due date of the payment |  |  |  |  |  |
|  |  |  | # (a) Time for Principal to rectify inadequate access (subclause 39.7(a)(i) |  | 14 days |  |  |  |  |  |
|  |  |  | # Not used |  |  |  |  |  |  |  |
|  |  | # Not used |  |  |  |  |  |  |  |  |
|  |  | # Key Personnel (clause 50) |  | [#Insert] |  |  |  |  |  |  |

| Annexure to the Australian Standard General Conditions of Contract for Design and Construct |  |  | Part B |  |
| --- | --- | --- | --- | --- |
| This form may also be used where the Principal is required to provide an unconditional undertaking, by substituting Principal for Contractor and vice versa, wherever occurring. |  |  |  |  |
| Approved form of unconditional undertaking (clause 1 – Security) |  |  |  |  |
| At the request of ACN ABN (the Contractor) and in consideration of ACN ABN (the Principal) accepting this undertaking in respect of the Contract for (the Project) ACN ABN (the Financial Institution) unconditionally undertakes to pay on demand any sum or sums which may from time to time be demanded by the Principal to a maximum aggregate sum of ($ ) |  |  |  |  |
| The undertaking is to continue until notification has been received from the Principal that the sum is no longer required by the Principal or until this undertaking is returned to the Financial Institution or until payment to the Principal by the Financial Institution of the whole of the sum or such part as the Principal may require. |  |  |  |  |
| Should the Financial Institution be notified in writing, purporting to be signed by for and on behalf of the Principal that the Principal desires payment to be made of the whole or any part or parts of the sum, it is unconditionally agreed that the Financial Institution will make the payment or payments to the Principal forthwith without reference to the Contractor and notwithstanding any notice given by the Contractor not to pay same. |  |  |  |  |
| Provided always that the Financial Institution may at any time without being required so to do pay to the Principal the sum of ($ ) less any amount or amounts it may previously have paid under this undertaking or such lesser sum as may be required and specified by the Principal and thereupon the liability of the Financial Institution hereunder shall immediately cease. |  |  |  |  |
| Dated at this day of 20 |  |  |  |  |
| Annexure to the Australian Standard General Conditions of Contract for Design and Construct |  |  | Part C |  |
| Deed of novation (subclause 9.2(c)) |  |  |  |  |
| This Deed made the day of 20 between (the Principal) of ACN ABN and (the Contractor) of ACN ABN and (the Subcontractor) of ACN ABN and (the Incoming Contractor) of ACN ABN witness that: |  |  |  |  |
| 1 Upon receipt by the Subcontractor of the sum certified by the Superintendent as owing under the prior contract described in the Schedule hereto: (a) the prior contract shall be discharged; (b) the Subcontractor shall release the Contractor from the further performance of the prior contract and from all claims and demands in connection with the prior contract; (c) the Incoming Contractor shall punctually perform the obligations of the Contractor under the prior contract as far as they are not performed. The Incoming Contractor acknowledges itself bound by the provisions of the prior contract as if the Incoming Contractor had been named in the prior contract; and (d) the Subcontractor shall punctually perform like obligations and be bound to the Incoming Contractor as if the provisions of the prior contract were incorporated herein. 2 The Principal and Subcontractor each warrant to the Incoming Contractor that: (a) subcontract work carried out to the date hereof is in accordance with the provisions of the prior contract; and (b) all claims and demands in connection with the prior contract have been made to the Contractor. 3 The Principal and Subcontractor each indemnifies the Incoming Contractor from all claims and demands of the Contractor, Principal and Subcontractor in connection with the prior contract. 4 A Dispute between: (a) the Principal and the Subcontractor in connection with the Superintendent's certification of the sum owing under the prior contract; or (b) the Incoming Contractor and the Subcontractor in connection with clause 1(c) or 1(d), shall be resolved pursuant to the provisions of AS 4903—2000 Subcontract Conditions for Design and Construct which for the purposes of this clause 4 are incorporated herein. 5 This Deed shall be governed by the laws of the jurisdiction stated in Item 8 of the Contract between the Principal and Contractor. |  |  |  |  |
| Schedule |  |  |  |  |
| In witness whereof the parties have executed this deed of novation by affixing their seals. |  |  |  |  |
| the common seal of the Principal was affixed to this document in the presence of: |  |  |  |  |
| Secretary/Director |  |  | Director |  |
| Name (please print) |  |  | Name (please print) |  |
| the common seal of the Contractor was affixed to this document in the presence of: |  |  |  |  |
| Secretary/Director |  |  | Director |  |
| Name (please print) |  |  | Name (please print) |  |
| the common seal of the Subcontractor was affixed to this document in the presence of: |  |  |  |  |
| Secretary/Director |  |  | Director |  |
| Name (please print) |  |  | Name (please print) |  |
| the common seal of the Incoming Contractor was affixed to this document in the presence of: |  |  |  |  |
| Secretary/Director |  |  | Director |  |
| Name (please print) |  |  | Name (please print) |  |

| Annexure to the Australian Standard General Conditions of Contract for Design and Construct Not Used | Part D |
| --- | --- |

| Annexure to the Australian Standard General Conditions of Contract for Design and Construct |  | Part E |
| --- | --- | --- |
| Deletions, amendments and additions |  |  |
| 1 | The following clauses have been deleted from AS 4902—2000 As provided in the marked-up version of the AS4902-2000 |  |
| 2 | The following clauses have been amended and differ from the corresponding clauses in AS 4902—2000 As provided in the marked-up version of the AS4902-2000 |  |
| 3 | The following clauses have been added to AS 4902—2000 As provided in the marked-up version of the AS4902-2000 |  |

| Annexure to the Australian Standard General Conditions of Contract for Design and Construct | Part F |
| --- | --- |
| Principal's Project Requirements |  |

| Annexure to the Australian Standard General Conditions of Contract for Design and Construct | Part G |
| --- | --- |
| Cost Plan |  |

| Annexure to the Australian Standard General Conditions of Contract for Design and Construct | Part H |
| --- | --- |
| Program |  |

AMENDMENT CONTROL SHEET

AS 4902—2000

Amendment No. 1 (2005)

REVISED TEXT

SUMMARY: This Amendment applies to Clause 37 (a) and (c) of Annexure Part A.

Published on 30 March 2005.

Standards Australia

Standards Australia is an independent company, limited by guarantee, which prepares and publishes most of the voluntary technical and commercial standards used in Australia. These standards are developed through an open process of consultation and consensus, in which all interested parties are invited to participate. Through a Memorandum of Understanding with the Commonwealth government, Standards Australia is recognized as Australia’s peak national standards body.  For further information on Standards Australia visit us at

www.standards.org.au

Australian Standards

Australian Standards are prepared by committees of experts from industry, governments, consumers and other relevant sectors. The requirements or recommendations contained in published Standards are a consensus of the views of representative interests and also take account of comments received from other sources. They reflect the latest scientific and industry experience. Australian Standards are kept under continuous review after publication and are updated regularly to take account of changing technology.

International Involvement

Standards Australia is responsible for ensuring that the Australian viewpoint is considered in the formulation of international Standards and that the latest international experience is incorporated in national Standards. This role is vital in assisting local industry to compete in international markets. Standards Australia represents Australia at both ISO (The International Organization for Standardization) and the International Electrotechnical Commission (IEC).

Electronic Standards

All Australian Standards are available in electronic editions, either downloaded individually from our web site, or via On-Line and DVD subscription services. For more information phone 1300 65 46 46 or visit Standards Web Shop at

www.standards.com.au

GPO Box 5420 Sydney  NSW  2001

Administration  Phone (02) 8206 6000 Fax (02) 8206 6001 Email mail@standards.com.au

Customer Service  Phone 1300 65 46 46 Fax 1300 65 49 49 Email sales@standards.com.au

Internet www.standards.org.au

ISBN 0 7337 3524 X	Printed in Australia

* See Preface

* See Preface