#### Schedule 1 - Statement of Requirements

Overview

Purpose

    - The role of the AEC is to deliver an Australian citizen's right to vote, as established and defined by the Commonwealth Electoral Act 1918 (CEA).

    - The AEC is responsible for conducting Electoral Events and maintaining the Commonwealth electoral roll. The AEC also provides a range of electoral information and education programs and activities. These activities take place at various venues and locations across Australia.

    - During an Electoral Event, high volumes of furniture and equipment are hired and purchased by the AEC for use by each Division and State office. Only limited notice of an Electoral Event can be provided to the Service Provider.

    - In this context, the purpose of this Statement of Requirements (SoR) is to state the AEC’s requirements for Services in support of Electoral Events and invite potential suppliers to provide a solution that meets part or all of AEC’s requirements.

About the AEC

    - The AEC has a three-tier office network structure comprising:

      - a National Office in Canberra;

      - 6 state and two territory offices; and

      - currently 150 divisions located at approximately 85 locations around Australia.

    - Additionally, for the conduct of an Electoral Event the AEC operates:

      - approximately 65 Out-Posted Centres predominantly in industrial buildings and warehouses;

      - approximately 7,500 Polling Places at venues such as local schools and local halls, etc.

#### Further information about the AEC can be found on its website: http://www.aec.gov.au.

Definitions

In this SoR, the following additional definitions are used:

| Out-Posted Centres | - a premises which is the centre of election operations for divisions; it is where the AEC undertakes resource-intensive activities. They are used across the entire election cycle, including pre-election, election weekend and post-election activities. These are temporary premises used by Divisions to conduct activities for an Electoral Event which are typically based in industrial buildings and warehouses. Often, vote counting which leads to an election result is conducted in Out-Posted Centres which may also be used as logistics hubs. |
| --- | --- |
| Polling Day | - the day specified for an Electoral Event. |
| Polling Place | - a generic label identifying where polling (voting) takes place. These include Static Polling Places, Pre-Poll Voting Centres or Interstate Voting Centres. |
| Pre-Poll Voting Centre or PPVC | - a venue declared by the Electoral Commissioner under subsection 200BA(1) of the CEA to be a pre-poll voting office for an Electoral Event that allows voting in person prior to Polling (Election) day. |
| Static Polling Place | - a venue appointed as a polling place under section 80 of the CEA to collect votes for a Division in-person and only accepts voting on Polling (Election) Day. |

Services

Description of the Services

    - The AEC is seeking suitable Service Providers to provide the following Services:

      - Hire of furniture (e.g. tables, chairs) and/or office (e.g. water dispensers, urns, mats, lockers, etc.) and warehouse operational (e.g. pallet jacks, shelving, fencing, etc. – note, warehouse equipment exclusively at Out-Posted Centres) equipment (see Schedule 3 Annexure D of the RFT for further details); comprising:

      - delivery and collection of furniture and equipment;

      - unpacking/repacking and assembling furniture and equipment;

      - removal and disposal of packaging material;

      - meeting the AEC’s timeframes for Services;

      - dedicated account managers for critical stages within an Election Period;

      - reporting on the Services; and

      - invoicing for the Services.

For noting: while ideally, the AEC would value Service Providers who can provide all the requirements noted in Schedule 3 Annexure D of the RFT (i.e. all types of furniture and equipment, to all types of operation (OPCs and polling places) to all locations) the AEC understands that this may not reflect the business model of all Tenderers.

As such, while it would value comprehensive offers (covering all operations, requirements and areas) the AEC still wishes to evaluate offers based on the industry specialisation and unique offerings reflected in the Tenderer’s submission. For example: furniture only offers, warehouse equipment only offers, purchase/l-buyback options, etc.

    - The Pricing Schedules in Schedule 3 Annexure D of the RFT reflect indicative usage totals for a future Event, while considering information from the most recent Event (Federal Election 2025), including:

      - a list of AEC locations and their demographic classifications

      - quantities

      - periods of hire.

Further indicative delivery graphics and profile information for statics can be found in Schedule 3 Annexure O of the RFT.

    - Delivery and collection of furniture and equipment to and from nominated venues and locations will generally be for fixed durations for all the required equipment. The delivery and duration requirement for some materials, however, will be staggered at OPCs (and possibly for other locations) depending on the needs for those locations (as an example, see ‘electoral furniture’ categories in the ‘Out-posted Centre’ tab of the spreadsheet template as part of Schedule 3 Annexure D of the RFT).

    - The AEC wishes to work with the successful Service Providers to develop efficient delivery patterns for furniture and equipment. This is also critical to assisting the AEC understand and plan for transport charges. Tenderers should factor time to work with AEC staff in each state to plan deliveries (e.g. milk runs) in the planning period directly prior to the election being called.

    - Dedicated account manager(s) should have an appropriate level of seniority in the Service Provider’s organisation who is readily contactable and is experienced in performing a client relationship management role. They would be the primary point of contact for:

      - managing the Services at a holistic level;

      - coordinating requests, Services and invoicing arrangements at the national level, where appropriate; and

      - addressing (and escalating where required) all correspondence, queries, complaints and concerns of the AEC Representative in a prompt and responsive manner.

    - The dedicated account manager must be available to:

      - liaise with the AEC Representative during Business Hours, after Business Hours, and on weekends during an Election Period; and

      - respond promptly to all AEC enquiries and requests.

    - An alternative contact person of equivalent seniority (or higher) must also be nominated by the Service Provider in the event that the dedicated account manager is not contactable.

    - On collection of furniture and equipment, the Service Provider must immediately notify the AEC if any AEC Material or Sensitive Election Material is found in the hired furniture or equipment. The AEC Material or Sensitive Election Material must be held securely by the Service Provider, until the AEC arranges for the collection of its material within 5 business days.

    - The Service Provider is expected to provide the Services in accordance with the AEC’s timeframes, specified in Table 1 below, noting the AEC will engage the Service Provider during planning stages in the lead up to a General Election to discuss this further. Final delivery timeframes will be confirmed prior to the requirement by the AEC in writing in a Work Order.

#### Table 1: AEC Delivery Timeframes for a General Election

| Timeframe |  | Description of Service |
| --- | --- | --- |
| Static Polling Places |  |  |
| 1. | No later than 7 days prior to commencement of each delivery | Service Provider to provide AEC with a delivery schedule for all Static Polling Places. |
| 2. | Ten calendar days prior to Polling Day | Commence deliveries of ordered items to Static Polling Places. |
| 3. | Three calendar days prior to Polling Day i.e. on the Wednesday immediately prior to Polling Day (with some ‘just-in-time’ deliveries up to one day prior to polling) - Please see Section 3 Annexure O of the RFT for indicative delivery patterns and further delivery profile information. | Complete delivery of the ordered items to Static Polling Places. |
| Pre-Poll Voting Centres |  |  |
| 4. | Four weeks prior to Polling Day | Service Provider to provide AEC with a delivery schedule for all Pre-Poll Voting Centres. |
| 5. | Four weeks prior to Polling Day | Commence delivery of the ordered items to Pre-Poll Voting Centres. |
| 6. | Three weeks prior to Polling Day | Complete delivery of the ordered items to Pre-Poll Voting Centres. |
| Out-Posted Centres |  |  |
| 7. | No later than seven days prior to commencement of each delivery | Service Provider to provide AEC with a delivery schedule for all Out-Posted Centres. |
| 8. | Between three and six months prior to Polling Day | Deliver the ordered items to Out-Posted Centres. |

    - Table 2 below provides an indicative schedule of the Services required from the Service Provider for the collection of hired furniture and equipment from Static Polling Places and PPVCs for a General Election.

#### Table 2: AEC Collection Timeframes for a General Election

| Timeframe | Description of Services |
| --- | --- |
| Fourteen days prior to Polling Day | AEC to provide the Service Provider with: - collection dates, including a list of priority collections to be undertaken on the first Monday after Polling Day; and - a list of locations excluded from the collection requirement. |
| Seven days prior to Polling Day | Service Provider to provide the AEC with a collection schedule. |
| Two days following Polling Day (first Monday after Polling Day) | Complete collection of furniture and equipment from polling places where priority collections are required. Commence collection of all other furniture and equipment from all polling places except those that have been excluded from this timeframe. Unless otherwise advised, collections from school premises must occur during normal school hours i.e. 9am to 3pm Monday to Friday. |

    - The AEC may request the following Additional Services:

      - storage of furniture and equipment owned by the AEC; and

      - delivery, collection and/or transport of furniture and equipment and incidental goods and services.

    - The AEC may purchase Goods from the Service Provider at the prices set out in the relevant Schedule to the Agreement. A separate work order under the terms and conditions set out in the Commonwealth Contracting Suite will be established should the AEC choose to purchase any Goods. The terms and conditions for the Commonwealth Contracting Suite is at https://www.finance.gov.au/government/procurement/commonwealth-contracting-suite-ccs#ccs-terms.

    - Additionally, the AEC wishes to consider options that involve the purchase of Goods from and sale-back to the Service Provider. The AEC asks Tenderers to use their industry expertise to develop options and provide pricing that allow the AEC to purchase the furniture and equipment and either retain that furniture and equipment, or, if there is no further ongoing requirement on the part of the AEC, for the Service Provider to arrange the pick-up and return of those items for a pre-agreed price.

      - Should the Tenderer wish to tender for this element, the relevant pricing schedule should be added to Schedule 3 Annexure D of the RFT. Pricing should include the purchase price, delivery (transport and handling) pricing, sell-back pricing and pick up (transport and handling) pricing and any surcharges based on the range of furniture and equipment noted in Schedule 3 Annexure D of the RFT.

Reporting

#### When delivering/collecting furniture and equipment, Service Providers must:

provide reports in a format, layout and style acceptable to the AEC.

provide daily reports during peak service periods. The content of these reports will include an itemised list of completed deliveries/collections of furniture equipment to the AEC Representative on a daily basis (via email) before 6:00pm local time;

notify the AEC Representative immediately of any variation to the delivery or collection schedules whether due to circumstances within its control or otherwise;

ensure it has sufficient transport capacity and resources to ensure optimal trip and capacity planning to ensure the minimum number of trips are made, including working with the nominated AEC representative to agree delivery and pick up timeframes prior to execution;

ensure that the AEC Representative is contacted prior to the delivery or collection of the furniture and equipment where it is anticipated that additional charges (including any surcharges, as noted in the pricing schedule) may apply, for example as a result of additional trips or weight.

Invoicing

#### Invoices must meet the requirements of a tax invoice as set out in the GST Act and contain the following information:

the details of the Services e.g. quantities/descriptions/locations/dates/times of the furniture delivered;

contract number;

period covered by invoice;

title and description of the Services;

the amount of any Fee Credits applicable during the invoice period;

surcharges (including details of those surcharges e.g. justification, location, dates, times) and

any other information reasonably requested by the AEC from time to time.

Service Levels

The AEC requires the Service Provider to meet or exceed agreed Service Levels as detailed in Table 3 with final measurement levels for Service Levels to be included in the proposed agreement.

Table 3 – Draft Service Levels

| No | Service Levels |
| --- | --- |
| 1 | Quality of furniture and equipment: Supplied items are fit for purpose for their intended use. Draft measurement level: 99.5%. |
| 2 | Timeliness of Supply and Delivery: Supplied items are both delivered and removed from the agreed locations within agreed timeframes. Draft measurement level: 98%. |
| 3 | Removal of Packaging Material: Packaging material is either removed from AEC controlled locations by the Service Provider or disposed of as agreed. Draft measurement level: 99.5%. |
| 4 | Invoice Accuracy: Invoices are provided on time and to agreed accuracy and content standards, including showing all agreed surcharges and levies. Draft measurement level: 99.5%. |

Note to Tenderers: The AEC will work with the Service Provider to develop a Service Level Agreement (SLA) based on the service levels above. The SLA will involve the application of fee credits should the Service Provider fail to meet the service levels. It is expected that the Service Provider will monitor and report on its performance with the intent to meet or exceed all service levels and actively identify any areas requiring improvement.

For further guidance on the AEC’s current thoughts on developing the Service Level Agreement, please see the Annexure A – Service Level Scenario.

##### Annexure A -  Service Level Scenario

- Background

  - The key constraint to achieving optimal outcomes for furniture and equipment hire concerns uncertainty around the timing of an Electoral Event i.e. the AEC cannot give clear notice of when the next General Election will be held. At this stage, the best information that can be provided to Service Providers on timing is that:

    - the earliest the next General Election can be called is 7 August 2027; and

    - the latest time that the next General Election can be called is 20 May 2028.

  - AEC will also provide guidance on subsequent Electoral Events including General Elections when known.

  - The Services will primarily be provided in support of three categories of venues with different levels of uncertainty surrounding their requirements:

    - Out-Posted Centres (OPCs): typically, premises for an OPC are leased for a longer period (e.g. 1 to 3 months) than PPVCs or Static Polling Places. As ballot papers are counted at an OPC they must be secure. There is higher certainty around the furniture/equipment requirements for an OPC.

    - Pre-Poll Voting Centre (PPVC): a polling place where an elector casts a vote before Polling Day. Typically leases for PPVCs are approximately 1 month. Premises leased are mostly community centres, schools and churches. Certainty around the furniture/equipment requirements for a PPVC is low but considered better than that for Static Polling Places noting that some PPVC locations will not be finalised until after the General Election announcement has been made.

    - Static Polling Places: polling places set up in each Division to take the votes of electors for an Election Event i.e. the venue where voters will turn up on Polling Day. Premises for Static Polling Places are often local schools and churches. Leases for Static Polling Places are very short meaning timeframes for delivery and collection of furniture will be limited (e.g. 1-2 days). Static Polling Places have the lowest level of certainty around their furniture/equipment requirements.

- Managing uncertainty

  - It is estimated that the AEC's requirements for approximately 80% of its furniture and equipment needs will be related to OPCs. Noting this, the AEC proposes to manage this uncertainty related to its OPC requirements by:

    - Engaging closely with Service Providers during planning stages. For example once leases for OPCs are finalised, the Service Provider will be provided the relevant details to help with the delivery/collection schedule; and

    - Work Orders for OPCs should be established relatively early in the lead up to a General Election i.e. several months prior to a General Election.

  - The AEC's furniture and equipment requirements for Pre-Poll Voting Centres and Static Polling Places are far more 'fluid' and cannot be fixed until after the announcement has been made. Noting that timeliness for delivery of furniture and equipment is critical, the AEC proposes to manage this uncertainty by:

    - Providing Service Providers maximum/minimum ranges for its furniture and equipment requirements;

    - Establishing Work Orders on a Not-To-Exceed basis and drawing down on their value as requirements become fixed;

    - Selecting Service Providers that will proactively engage with the AEC to actively manage uncertainty and risk.

- Service level agreement

  - As Polling Day draws closer, Service Providers may be unable to meet the AEC's requirements if they have been given insufficient time and the AEC's options to approach alternative suppliers will be restricted.

  - To reduce the likelihood of this scenario and to better align the interests of the AEC and the Service Provider, a Service Level Agreement is at Schedule 4 of this Deed.

  - For the purposes of developing an effective Service Level Agreement an example of an optimal outcome for Static Polling Places in a Division is provided below.

Example of Optimal Outcome for Static Polling Places in a Division

    - An Election Event is announced and the Service Provider is notified. Within 7 days, most of the orders confirming the AEC's requirements are confirmed for each location within the Division. However, some orders can only be provided closer to Polling Day.

    - Service Providers coordinate the necessary furniture and equipment in line with AEC requirements.

    - Furniture and equipment is delivered to Static Polling Places with all deliveries being finalised by 8pm on the Friday before Polling Day (Saturday).

    - At delivery, the Service Provider unpacks the furniture, assembles the furniture, moves it to the approximate vicinity of the desired place within the Static Polling Place and then removes all packaging material.

    - Furniture and equipment is marked/labelled as belonging to the Service Provider.

    - The Service Provider obtains approval/signature from the nominated AEC representative at the site that the furniture/equipment has been delivered.

    - By 6pm on each day during the 2 weeks leading up to Polling Day, the Service Provider emails the relevant AEC representative of all furniture and equipment that has been delivered (Delivery Report). However, on the Friday before Polling Day, 2 Delivery Reports are provided: one at 1pm and one at 9pm.

    - The day following Polling Day (Sunday), collection of equipment commences at venues where this is possible - some venues may be unable to facilitate collection on Sundays. Photos are taken of any damaged furniture or equipment.

    - All furniture/equipment has been collected by the second day following Polling Day (Monday).

    - By 6pm on each collection day, the Service Provider emails the relevant AEC representative of all furniture and equipment that has been collected which includes details of any missing furniture/equipment as well as photos of damaged equipment (Collection Report).

    - In the following weeks, an invoice is then sent by the Service Provider to the AEC detailing all furniture and equipment that has been delivered and collected from the relevant sites. The details in this invoice can be clearly

  - Some potential factors leading to sub-optimal outcomes in this example are provided below:

    - The Service Provider is unable to meet the AEC's requirements for furniture and equipment in terms of quality and quantity leading to the AEC approaching other suppliers;

    - Faulty furniture or equipment is reported to the Service Provider but action taken to replace the faulty equipment is delayed;

    - Furniture and equipment is not marked accurately which leads to confusion during collection and preparing Collection Reports;

    - Invoices provide insufficient detail and do not reconcile with Collection Reports or Delivery Reports, including surcharges and levies.